Postgraduate Conference

Handbook

2015/16

Contents

Introduction									4

Postgraduate Conferences						4

Terms & Conditions							4

Why Organise a Postgraduate Conference?				5

Strategic Conference Planning						6

The Creation of an Idea						6

Making Key Decisions						6

Creating a Conference Team/Committee				6

Applying for Funding							7

Artsmethods@manchesterConference Funding			7

External Funding							8

The Conference Timeline						8

Building a Conference Programme					10

Call for Papers							10

Organising Sessions/A Running Order				10

Approaching Keynotes						11

Marketing & Publicising the Conference				11

Posters								11

Email list								11

Blogs									11

Networks								12

Twitter									12

Budgeting & Financial Procedures					12

The Budget Holder							12

Account Codes							12

Expenses								12

Organising Committee Expenses				12

Delegate Expenses						13

Income								13

Invoices & Payments						13

Online Payments						13

Cash & Cheques						13

Budget Updates						13

Room & Venue Hire							14

Venues on Campus							14

Alternative Venues in Manchester					14

Catering & Refreshments							14

University Catering							14

Approved Suppliers							14

Rules on Serving Alcohol						15

Managing Bookings							15

eStore									15

Delegate fees								16

Cancellation Policy							16

Delegate Packs								16

Health & Safety								16

Writing a conference report						16

Handing over to a new conference committee			16

Useful Contacts								17

Postgraduate Conference Handbook 2015/16

Introduction

Postgraduate Conferences

Organising a successful postgraduate conference is a considerable undertaking.  This handbook has been produced to provide comprehensive guidance for postgraduates in the School of Arts, Languages & Cultures who are in the process of applying for or are in receipt of postgraduate conference funding.  This document will explore the life cycle of a conference and suggest several approaches for organising a successful event.  It also includes information on policies and procedures that are currently in place at the University of Manchester, although please note that conference organisers are expected to check the University website regularly for updates to University policy.

It is expected that conference organisers will refer to this handbook to answer any queries that they may have before seeking any further advice or guidance from artsmethods.

Terms & Conditions

As part of the terms and conditions for receiving funding conference organisers must assume full responsibility for ALL administrative duties pertaining to the conference.  Conference organisers must sign the artsmethods conference policy form to indicate that they have read and understood these terms and conditions.  Such responsibilities include:

The conference organisers must undertake:

- To refer to the information included the Postgraduate Conference Handbook and on the “Funding” section of the artsmethods@manchester website before seeking further advice for general queries

- To consult with the artsmethods@manchester administrative assistant who can provide ad-hoc guidance and support

- To monitor the income and expenditure for the conference or initiative and to keep all financial and budget records (invoices, receipts, spreadsheets etc)

- To liaise with the University’s finance office to administer cash, cheques, invoices and any payments as well as income and expenditure for the conference

- To put in place sound administrative procedures for the conference or initiative

- To apply to external organisations to supplement conference/initiative income and arrange for this income to be paid into the University

- To book the venue and rooms, if appropriate

- To book all catering and refreshments, if appropriate

- To order all stationery and supplementary materials, if appropriate

- To liaise with all keynote speakers and delegates, where appropriate

- To respond to all queries regarding the conference/initiative

- To advertise/publicise the conference in the wider research community – this should include external networks – and provide comprehensive information for the artsmethods@manchester website

- To regularly maintain any web-based interface for the conference/initiative, including any websites, blogs, twitter feeds

- To produce ad-hoc financial and administrative updates to artsmethods@manchester

- To produce a conference/initiative report within 30 days of the event taking place (this will be put on the artsmethods website)

- To provide photographs or any other materials which arise from the conference/initiative, for publicity and reporting purposes

- To produce a final budget at the end of the conference

- To send copies of all receipts/invoices to artsmethods@manchester

- To manage the conference/initiative budget in a way which minimises the likelihood of any shortfall

- To take responsibility for the likelihood of any shortfall in funding, notifying the artsmethods@manchester budget holder, as appropriate

- To abide by the University’s Health & Safety policy, as outlined on the University website and in the conference handbook

The University’s policies and procedures can be complex. The organising committee is expected to meet with the artsmethods administrator to discuss the plans for the conference.

Why organise a postgraduate conference?

Postgraduate conferences are extremely rewarding, offering organisers the opportunity to make a vital contribution to the postgraduate community in their discipline.  Postgraduate conferences play a central role in the research community, providing the opportunity for postgraduates to present their research in a supportive setting and raising the profile of the University and department.  At the same time conference organisation contributes to the development of knowledge, ideas and skills that are essential to the process of research at early career level, as well as representing an important occasion for the development of transferable skills.

Nevertheless, postgraduate conferences require a significant investment of time, energy and effort on the part of the conference organisers.  Many successful conferences tend to appoint an organising committee of fellow postgraduates who are willing to share responsibility for the administration and organisation of the conference.  Working as part of a conference team also has its rewards: the opportunity to collaborate, to share ideas, to develop interdisciplinary perspectives and to share the administrative burden.

Organising a conference requires the following capabilities:

- Decision making

- Team working and collaboration

- Project and time management

- Negotiation

- Administration and events management

- An appreciation of policy and strategic frameworks

- Leadership

- Networking

- Knowledge dissemination

- Marketing, communication and use of web 2.0

- Presentation

- Developing a research and publication profile

- Financial management

- Problem solving

- Ability to acquire internal and external funding/grants

- Public engagement (where applicable)

Strategic Conference Planning

The Creation of an Idea

There are some postgraduate conferences in the School that have been organised for several consecutive years.  Inheriting an already established conference from a previous organising committee can be one way of ensuring that you get the opportunity to organise the conference in the forthcoming academic year (and contribute to keeping it sustainable).  Nevertheless, you might have an idea/theme of your own which you would like to explore and therefore decide to establish your own postgraduate conference and commit to making it sustainable.  Exploring research methods and research methodology must also be a significant part of any postgraduate conference.  Conference sustainability is important for a number of reasons:

(a) It ensures that future postgraduates have the opportunity to oversee the administration and organisation of a postgraduate conference

(b) Discussions amongst the established postgraduate network continue to develop

(c) Postgraduate conferences bring additional income into your discipline.

Making Key Decisions

When exploring whether or not a theme is suitable for a postgraduate conference you might like to consider the following:

- What is the scope and purpose of your conference?  What are your aims and objectives?

- Will it explore current research methods/trends in the discipline?

- How will the conference be structured?  Who will attend and who will present?

- Where will the funding come from?

- What are the appropriate dates/times/venues to hold the conference?

- Who else is talking about the theme?  (e.g. the public, the government, academics, postgraduates?)

- Why is the theme currently popular?  What are the benefits of exploring this theme in a postgraduate conference?

- Is the theme interdisciplinary?

- How will the conference benefit the research community in the School?

- Will there be opportunities to publish papers from the conference?

- How will the organising committee approach and engage delegates?

- What will be the outputs from the conference?  What will be the overall contributions to the discipline/field?

- What keywords would you associate with the conference topic/theme?

Creating a conference team/committee

Postgraduate conferences always rely on a team or a committee to ensure that proceedings run smoothly.  You might consider also recruiting a number of volunteers who can help you on the day with tasks such as handing out delegate packs, manning the conference reception desk (see timeline).  Any call for volunteers for election onto a conference committee should outline the purpose of the team as well as a description of the roles within that team.

At the first meeting of the committee ensure that “team roles” is a point for discussion on the agenda.  This will help to dispel any misunderstandings about roles and responsibilities – and can also help members to reach agreement on the tasks and procedures ahead.  All committee members must be available in the run-up to the conference.  Conference committees will usually include the following roles (some roles are smaller and so one person might have responsibility for two roles rather than one).  For smaller committees, roles are usually divided up accordingly.

- A head of conference/team – with overall responsibility for running the conference, ensuring that the project runs to time and within budget and leading the other committee members to ensure that they manage their tasks adequately and on time.

- Budget holder – with responsibility for establishing and monitoring the budget, organising fees and expenses, seeking funding and working out costing

- Programme coordinator – with responsibility for coordinating and collating the conference programme, establishing contact with keynotes, delegates and other interested parties to draw the programme together, responsibility for originating the call for papers and sifting through applications

- Facilities manager – with responsibility for organising the conference venue, catering, bookings, AV equipment and receptions.  This facilities manager will also be responsible for tea/coffee breaks, restaurant bookings and other social/networking activities

- Webmaster/technical support – with responsibility for creating and maintaining the webpage/blog

- Marketing manager – with responsibility for creating a marketing and publicity strategy for the conference, maintaining the contact database, managing the flyers/posters, email marketing and setting up listserve

- General administrative manager – with responsibility for organising the overall administration of the conference, handling queries, helping other members of the team and managing events on the day

Applying for Funding

Every academic year artsmethods@manchester launches a conference funding competition, details of which will appear on the artsmethods blog (http://artsmethodsmanchester.wordpress.com/) and announced via the Twitter feed: http://twitter.com/ArtsmethodsManc.  The fund offers support of up to £500 for each successful conference application.

It is expected that conference organisers will approach other funding bodies (e.g. the Institute of Historical Research or the Renaissance Society) and publishers (e.g. Routledge) to offer additional funding for the event.  Occasionally external funding bodies offer support the conference on the understanding that the money is allocated to support a particular element of the proceedings.  For example, publishers usually donate money as a “Conference Marketing Fee” which goes towards the inclusion of posters and flyers from their company in the conference delegate packs.  Usually funding bodies require that their logo be placed on all conference marketing materials (printed and online) to demonstrate that they have supported the event.  Some funding bodies offer money to put towards conference delegate bursaries – it is crucial that the organisers administer this money in the correct way (please see the Finance section for further details).

artsmethods@manchester Conference Funding

There are various terms and conditions attached to artsmethods funding for postgraduate conferences.

What can the money be used for?

- To fund venue and room hire

- To fund refreshments and catering

- To cover the expenses (e.g. travel and accommodation costs) for the keynote speaker(s)

- To cover the expenses (e.g. travel) for the organising committee members

- To fund stationery and other materials for the conference

- To fund marketing materials for the conference

The money must NOT be used:

- To pay the conference organisers a fee or honorarium for their time

- To pay a conference fee or honorarium to the keynote speakers

- To provide delegate bursaries for the conference

- To fund a wine reception for the conference (it is expected that the organisers will charge a nominal delegate fee to cover this expense)

- To provide travel bursaries for the delegates (in situations where the committee members secure external funding for travel bursaries, delegates must pay for their travel in advance and claim it back it is expected that the funding for the travel bursaries be paid into the account in advance to cover these expenses)

External Funding

Many other organisations offer funding towards the organisation/administration of postgraduate conferences.  These organisations include publishers such as Routledge and not-for-profit organisations, research councils such as the Renaissance Society, the Royal Historical Society and the Arts & Humanities Research Council (AHRC).  Details of any schemes are usually available on their website.  Some bursaries stipulate that the money must be spent on a particular activity e.g. conference marketing/publicity, delegate travel bursaries and delegate fee bursaries.

*Please note – where funding has been secured to fund delegate travel bursaries the delegates must pay for their travel in advance and claim them back using an expenses form in the usual manner. Original travel tickets/receipts must be supplied along with the signed expense form.  The University is unable to support the advance payment of travel expenses or providing cashback on the day.  The procedure for paying delegate fee bursaries is extremely complicated and involves assessment of income and HMRC regulations – please speak to a member of the University finance office to negotiate the best procedure to support this*

The Conference Timeline

Planning is part of a systematic and cyclical process which leads to action (or doing) and reviewing.  99% of conference successes are down to correct and strategic planning and some of these can take anything up to a year in advance – it’s not a problem if you don’t have as much time as that, the chances are that the planning actually started as an idea several months or weeks ago before formally morphing into a plan for a conference.  Sustainable conferences are successful because they are rigorously reviewed before the new conference team beginning planning for the next event.

Conference timelines/deadlines outline the fundamental factors involved in most conference planning schedules:

One Year Before

- Decide on conference theme and format (start/part of a series?)

- Decide on conference committee and distribute roles (administration – phone numbers/addresses)

- Decide on any post-conference publishing (journal special issue, CD, website)

- Seek help/support/advice (Researcher development, department heads, supervisor, fellow postgraduates)

- Decide on a date (check that there is no overlap with related conferences elsewhere). Be aware of possible out of hours/weekend charges for Portering services from Estates.

- Identify and contact key speakers/workshop or masterclass presenters

- Release a general call for papers

- Plan preliminary budget (AV equipment, portering can cost extra)

- Apply for funding support (from various sources)

- Contact publishers for book displays/flyers

8 months before

- Book venue – it is highly recommended that the SALC Graduate School training room is used; it is a large room that allows catering and is free of charge Mon-Fri. Ask the SALC PGR office for availability.

- Plan accommodation options

- Prepare posters and publicity material

- Identify possible participants and delegates and build a database of contacts

- Prepare website/blog, mailing list/listserve and on-line booking facility (see below)

- Set up/access conference email account

- Advertise conference generally

6 months before

- Display posters

- Send poster to interested parties (by email)

- Distribute details/publicity materials on mailing list/listserves and useful contacts

- Liaise with finance to check procedures

- Close call for papers

- Create preliminary programme

- Liaise with speakers and keynotes about travel arrangements

- Plan post-conference publishing

3 months before

- Book catering – restaurants and on-campus catering (see catering and refreshments)

- Confirm AV equipment requirements with speakers

- Book AV equipment

- Reserve accommodation for speakers

- Confirm travel arrangements with speakers

- Contact the University Press Office

- Check out of hours access if not using a hall of residence – you may have to allow some money in your budget for a porter to be available

- Prepare/update delegate database and mailing list for easy communication and group instructions (BCC:)

- Redistribute details on listserves

- Complete preliminary programme

- Arrange staffing for conference reception desk

1 month before

- Send programme to all delegates, maps and directions by email

- Confirm accommodation (unless booked by delegates)

- Confirm restaurants/catering and any special dietary requirements for speakers/delegates

- Check for local publicity for conference packs

- Organise chairs/respondents/commentators for sessions

1 week before

- Reconfirm food numbers

- Prepare conference packs

- Prepare name badges

- Confirm AV needs

- Prepare directional signage

- Confirm staffing for desk

- Organise water/jugs/glasses, tablecloths etc

- Organise people to move furniture if rooms need rearranging

- Prepare expense form envelopes with thank you notes

- Confirm chairs/respondents/commentators

- Deadline for AV presentations to be submitted?

1 day before

- Check rooms for cleanliness

- Organise water for speakers

Morning of conference

- Put up directional signage

- Set up registration desk

- Set up and test AV equipment

- Give speakers expense forms

- Take photos for publicity (conditions of funding)

Day after

- Send out thank you letters

One week after

- Prepare post-conference publicity

- Write up conference experience for funding sources

- Send out call for papers to be published

- Identify who to hand over the conference organisation to for the forthcoming conference

Building a conference programme

Call for Papers

As mentioned above, those who have decided to organise a conference usually have a conference theme in mind.  Once a theme has been decided upon, the conference organising committee usually send out a call for papers (including a deadline) across their academic and professional network, inviting expressions of interest to present a paper at the conference.  Proposals usually outline the working title of the paper and a short abstract of its contents.  Organising committees occasionally include in the call for papers an indication of the types of papers that they will be accepting.  For example, “the organising committee will give especial consideration to papers which explore the theme of * within an interdisciplinary context”.  Guiding principles such as these help those who are interested in presenting their work to deliver a paper that fits in with the overall theme(s) of the conference.  It also helps to ask potential participants to categorise their papers and to include keywords and principles.  This helps when deciding which papers to accept and where to place them in the programme.

Organising Sessions/A Running Order

Once the deadline has passed the organising committee will sift through the applications and decide which papers to accept, which to hold in reserve and which ones to reject (if any).  After this time, the organisers will divide up the papers into panels or into a running order depending on the contents of the papers.  Matching up papers to form a panel can sometimes be difficult although some organising committees usually organise papers according to subject matter, time period, methodology, theme etc.

Approaching keynotes

Most postgraduate conferences have one or two keynote speakers who address the whole conference at the beginning of proceedings and give a keynote speech relevant to the conference theme.  It is usually apparent to most conference organisers which academics they would like to approach to give a keynote address.  Most academics are happy to be keynote and their expenses (travel) are usually reimbursed. If accommodation is required, it is highly recommended that MBS Hotel is used (see ‘Accommodation’ for details). Please note that the University is not in a position to pay a keynote speaker (or any other conference speakers) an honorarium for their time.  It is always worth considering having a back-up keynote speaker in mind just in case the keynote has to pull out at the last minute.  Recruiting the keynote speaker well in advance can help to avoid some of the hassle should they have to pull out.  Once you have approached a keynote and they have accepted, keep them briefed with regular updates about the conference.  Be careful to explain to them what the conference is about and outline how you plan to ensure that the conference is a success.  If there is anything you want the keynote to focus on particularly during their speech then it is a good idea to do this at an early stage.

Marketing and publicising your conference

Posters

Posters usually accompany the Call for Papers and invite expressions of interest from those delegates who wish to attend by asking them to pre-register their intention to attend.  Posters are an inexpensive way to advertise a conference and can be emailed as a PDF attachment as well as being added to a website or a blog.  Posters should be visually appealing and include the date, time and location as well as the address for any blog or website and details of how to register/contact the organising committee.  Posters can be printed at several outlets across the University using an appropriate account code to charge.  The main humanities printing services are in the Kilburn Building (print room) and the Graphic Support Workshop (gsw@manchester.ac.uk).  Alternatively poster costs can be kept down by simply photocopying the original.

Email List

Any expressions of interest, both from potential presenters and potential attendees, should be added to a mailing list or database of contacts which should be regularly updated and managed.  It’s useful to set up a unique email address for the conference e.g. renaissance2012@gmail.com to manage all the conference email traffic.  These email lists can be useful when sending out email reminders and distributing any administrative information such as the formal conference programme and any changes in venue or date.

Blogs

Many conference organisers prefer to set up a blog instead of a website because they are easy to update and users can leave comments.  This can enable discussion between delegates before the conference and it can also encourage the discussion to continue between delegates once the conference is over.  Wordpress is a very user friendly blog platform, offering pre-made templates and a dashboard to manage the blog and comments.  Widgets can be added to the blog such as a tag cloud and categories.  There can also be a calendar of past blog posts and a widget to link to the conference Twitter feed (see below).

There are also various established blogs across the Humanities which can advertise your conference to postgraduates and other interested parties – please email artsmethods@manchester.ac.uk  details of the conference. This will then be added to any Humanities bulletins and distribution lists.

Networks

Conferences should be advertised through research networks across the UK.  In the early stages of planning the conference organising committee should be able to identify which networks are appropriate and make contact with organisations to advertise that the conference is taking place.

Twitter

Academic conferences are now using twitter to advertise updates regarding the conference and to create a dialogue between the organisers and the delegates.  Twitter accounts can be set up swiftly and the committee can start to follow other tweeters, especially those who are in associated research networks.  Conferences can create their own hashtag e.g. #renaissance2012 – this hashtag can be added to any conference tweets and viewed by the committee and other delegates.  The hashtag can be used to report discussion during the conference and interaction between delegates and also to update those who cannot attend.  Twitter accounts can synchronise with blogs (e.g. Wordpress) and websites where users can view recent tweets about the conference.  The delegates can be made aware of the Twitter feed and associated hashtag on the conference poster and programme – e.g. “Keep track of conference updates by following @renaissance2012 and tweeting with the hashtag #conference2012”.

Budgeting & Financial procedures

The Budget Holder

The organising committee are responsible for liaising with the artsmethods administrator to ensure that all income and expenditure is monitored accordingly.

Account Codes

Please liaise with the artsmethods administrator for details of the account code – you will need this information when booking catering or supplies through the University.  If an eStore account is being set up to deal with delegate fees, a separate account code is needed, this is generated by the school accountant. Contact the artsmethods administrator for further information.

Expenses

Organising Committee Expenses

It is feasible that members of the organising committee will incur expenses when organising the conference.  These should be realistic and kept to a minimum.  The University is unable to pay the organisers for their time (i.e. an organising fee) but will reimburse reasonable expenses such bus/taxi fares provided that these have been agreed with the budget holder in advance and are accounted for in the budget.  Please note that it takes between 4-6 weeks for expenses to reach the nominated account.  When paying for items for the conference, please make sure that there is money to cover this should there be a delay in payment as the University is not in a position to reimburse any expenses incurred through delay in payment (e.g. credit card charges).

Delegate Expenses

The organising committee will have to decide what reasonable delegate expenses can be reimbursed.  For example, the conference might have received funding to cover the cost of delegates’ travel.  The appropriate form will depend on the nature of the money being claimed – for those on the University payroll (usually members of staff and GTAs) the form (PR5) is now online and available from the Staffnet portal.  For those not on the University payroll, the form is a PR7 expenses form.  All forms are available to download from the University StaffNet website. If in doubt, please contact the appropriate finance assistant (http://www.humanities.manchester.ac.uk/humnet/facserv/finance/) who will check the system and confirm.

Income

Invoices & Payments

In the event that the conference secures external funding, this money will be payable into the University account to be drawn upon by the conference holders.  In some circumstances there are additional regulations (e.g. in the case of delegate fee bursaries).  Please speak to the appropriate member of finance to ensure that all procedures are followed correctly.  The University finance office is able to raise invoices to send out to external organisations to ensure that the money be paid into the appropriate account – again please liaise with finance to get a list of the information required.

Online Payment

If you are charging a delegate fee to cover the additional costs of the conference (and associated wine reception) then it is highly recommended that you set up an account with eStore http://estore.manchester.ac.uk/ which is the University of Manchester’s online payment system. eStore allows delegates to pay fees and accommodation costs online and the money is paid directly into the appropriate account. Contact the artsmethods administrator for further details.

Cash & Cheques

Conference organisers might also have responsibility for handling cash and cheques associated with the conference.  Details of handling cash transactions can be found here: http://www.staffnet.manchester.ac.uk/services/finance/cash-transactions/.  For cheques and cash, budget holders are asked to keep a running list of the name of the delegate and the amount of money paid.  For cheques, it is also advisable to make a note of the date and the cheque number.  This sheet must be taken along to the Income Office (in the John Owen’s Building – only accessible with a valid student ID card).  Cash and cheques should not be left lying around and must be paid into the University account in at your earliest convenience.  The Income Office will present a payment receipt.  This must be given to the budget holder, alongside a copy of the list of payment details.  Organisers should provide delegates with a receipt for their payment.

Budget

Committee members are asked to create and maintain a rolling spreadsheet of costs (income vs. expenditure) and keep the account holder regularly updated as to what transactions should be coming in and out of the account.  Where possible it helps to obtain a final figure for catering, room hire etc so that these can be factored in before any variable costs.  Catering numbers don’t have to be finalised until several days before the event but it is best to err on the side of caution when selecting how many delegates are likely to attend the conference.

Room and venue hire

Venues on Campus

It is highly recommended that the SALC Graduate School space in Ellen Wilkinson is used for events.  There is a reception area and large room that’s allows catering. Please see the SALC Grad School office for availability and booking.

Rooms are available to hire across the University through the Central Teaching Spaces Team.  Organisers that have a staff email address are able to book rooms directly through the cts@manchester.ac.uk. Those who have a student email address will need to send their requests through to the artsmethods administrator.

Venue hire is free of charge; however, out of working hours and weekend bookings will incur portering charges from Estates. Normal operating hours are between 9am and 5pm, Mon - Fri.  You might consider holding a wine reception near to the rooms/venues but this will be subject to following the appropriate procedures.  In some cases it is possible to book foyer areas for refreshments – e.g. in the Samuel Alexander building.  For more details about booking please follow this link: http://www.estates.manchester.ac.uk/services/centralteachingspaces/

The majority of rooms on campus do not allow catering. If you are planning to have catering please specify this when requesting a room.

Alternative Venues in Manchester

It is possible to host the conference at an alternative venue, away from the University campus; however, the venue has to be on the University’s system as an approved supplier, in order to guarantee payment. In the past conferences have been hosted at Chetham’s Library, the John Rylands University Library (Deansgate), the MOSI, and the Anthony Burgess Foundation.  The organising committee should reach an agreement on the appropriateness of the venue for the conference (taking into account the dates, times costs and requirements).  It is worth contacting the venue in advance to find out if they can accommodate your conference and how much the hire charge is.  Please note that some venues stipulate that their in-house caterers must be used when booking venue hire.

Accommodation

For speakers accommodation, it is highly recommended that MBS Hotel is used (approx £50 b&b). As MBS are internal suppliers, the cost is paid by the account code. If an alternative hotel is used, the speaker is required to cover their own costs upfront and claim back on expenses.

Catering and Refreshments

University Suppliers

The University has its own in-house catering company, Food on Campus.  Food on Campus is automatically set up to receive orders from University staff and students, upon presentation of an account code.

Approved Suppliers

The University has a database of approved suppliers, including catering suppliers and restaurants (see below). These suppliers have been approved by the University based on quality of service and cost. Being in receipt of conference funding from the school means that you agree to act responsibly with public money and organising committees are therefore accountable for the way in which that money is spent.

- Approved suppliers for Catering:

- Food On Campus/Taste Manchester - http://www.tastemcr.com/

- Cafe Rylands, Cafe Muse, Christies Bistro - http://www.chancellorscollection.co.uk/

- Impact Catering - http://www.impactcatering.co.uk/

- KRO Catering (Ruby and Ruby) - http://www.krocatering.co.uk/

- Le Mange Tout - http://www.lemangetout.co.uk/

- Celia Clyne Banqueting Ltd - http://www.celiaclyne.com/

- Green Plate - http://www.greenplate.co.uk/

- Small word café (International Society) -  http://www.internationalsociety.org.uk/SWC%20home.htm

Pre/post conference meals

There are a number of restaurants on the approved suppliers list. Organisers should always liaise with the restaurant to arrange a set meal and price a few weeks prior to the conference in order for a purchase order to be raised so the University can invoiced. Under no circumstances can the University be invoiced without a purchase order.

- Approved restaurants (these are subject to change, check with the artsmethods administrator)

- Efes Restaurant

- Don Giovanni

- Little Yang Sing

- Red Chilli

- The Cornerhouse

If you need more information or specific advice, contact the artsmethods Administrator.

Rules on Serving Alcohol

Not all University venues allow you to serve alcohol or have wine receptions.  When making a booking with the Central Timetabling Unit or another venue provider it is a good idea to clarify whether the rooms you are requesting allow alcohol to be served.

Managing Conference Bookings

eStore

If you are using eStore to manage online bookings (see above section on Online Payments), the interface should tell you how many people have registered for the conference.  eStore can be used to update information about the conference.  For more information visit www.estore.manchester.ac.uk.

In order to use eStore, a finance account code for your event will need to be set up, if there is not one already existing from previous years. This might take some time so it is advisable to start planning and requesting well in advance. Contact the artsmethods administrator for further details

Delegate Fees

Delegate fees, even nominal charges such as £10 or £15, can ensure that the conference is well-attended.  People are more likely to turn up to the conference if they know that they have paid some money to be there.  Typically those conferences that have no attendance charge find that they lose a substantial amount of money due to last-minute cancellations and where no new delegates can attend in their place.  Many conferences use this fee to provide a wine reception at the end and many delegates are more than happy to cover this if they are told, in advance, why there is a charge.

Cancellation policy

The organising committee will have to manage bookings up until the start of the conference.  A cancellation policy helps to keep track of numbers, especially in the run up to the conference where arrangement of and payments for catering are usually finalised.  A typical cancellation policy will provide the delegate with a refund of their conference attendance fee up until 30 days before the conference date.  Those who cancel within 30 days of the conference usually forfeit their fee.  This ensures that last-minute cancellations are limited and that any charges associated with the delegate place can be covered.  It also ensures that the committee do not over-cater for delegates which can incur quite high charges.  A cancellation policy will prevent this from happening and ensure that delegates contact the committee to withdraw their attendance rather than simply not turning up.

Delegate Packs

Delegate packs give the conference a professional feel for the delegates.  At the very least, multiple copies of the conference programme should be available from the reception point for the conference.  The costs of the items ordered will be discussed with the conference organisers, and must always be covered in the conference budget.

Delegate packs usually contain the conference programme, flyers, useful information, a campus map, information about the venue and the city, use of WiFi and internet access (where possible) and a list of useful contacts.

Health & Safety

Conference organisers are bound to abide by the University’s Health & Safety policy.  Organisers must ensure that all attendees register correctly, on a daily basis, throughout the Conference.  Organisers must also acquaint all attendees with all safety and evacuation procedures, including when/where a file alarm will be tested in the venue (where appropriate).  Organisers will take all precautions possible to abide by all fire regulations, whether statutory or otherwise, and leave all fire points and accessories unobstructed and available for immediate use.  All gangways, staircases, passages, entrances or exits within the premises must be free from obstruction at all times.  Organisers must also ensure that all attendees comply at all times with these conditions.

Writing a conference report

It is usually a requirement of conference funding that the committee write a report which outlines how they have spent the money and what was gained from the day.  This helps to assess the impact of the conference and also dictates whether a similar conference will be funded in subsequent years.  Conference reports need be no longer than 1-2 pages of A4 and outline, in brief, the outcomes of the conference such as publications, discussion.  If any pictures are available from the event please include these in the report.

Handing over to a new conference committee

If your conference is a success then it will usually be sustainable.  To ensure that a similar conference runs in subsequent years many organising committees recruit a new conference committee and provide a formal handover to ensure that all administrative procedures and associated networks are maintained.

Useful Contacts

Dr Jerome Brillaud

Director of Research Training

School of Arts, Languages and Cultures

Jerome.brillaud@manchester.ac.uk

0161 2753227

Nicola Sheehan

Researcher Development Administrator

artsmethods Administrator

Tel: 0161 306 1113

artsmethods@manchester.ac.uk

Hannah Mansell

SALC Conference Organiser

Hannah.mansell@manchester.ac.uk

[Acknowledgements: many thanks to Hannah Mansell of the Martin Harris Centre and Melissa Markauskas, PhD student in Classics, for their helpful input into this handbook]