## Sheet1
| September | October | November | December | January | February | March | April | May | June | July | August
Accommodation brochure | September: PDFs to contributors 2nd proofs out Sign off from contributors; October: Final sign off from stakeholders Delivery; July: Kick off meeting / discuss successes/ issues of last year; August: Text editing and proofing process Design concepts
International Advantage | September: PDFs to contributors 2nd proofs out Sign off from contributors & stakeholders; October: Print, delivery; June: Kick off meeting / discuss successes/ issues of last year; July: Contributors to edit, sort out profiles and photography; August: Text editing and proofing process Design concepts
Home Advantage | September: PDFs to contributors 2nd proofs out Sign off from contributors & stakeholders; October: Print, delivery; June: Kick off meeting / scoping of project; July: Contributors to edit, sort out profiles and photography; August: Text editing and proofing process Design concepts
Undergraduate Prospectus | Send out info for updating | Copyediting and interviews | Text editing and proofing process Design concepts | PDFs to contributors 2nd proofs out Sign off from contributors | Final sign off from stakeholders | Print Delivery |  |  |  |  | Kick off meeting / discuss successes/ issues of last year | Follow up on ideas etc
Armitage fitness campaign (Crimbo) | October: Design ideas / production schedule / photography; November: PDFs to contributors / Final sign off from stakeholders; December: Print Delivery
Undergraduate Pocket Guide | October: Kick off meeting / discuss successes/ issues of last year; November: Text editing and proofing process Design concepts; December: Course listings and proofing; January: Final sign off from stakeholders; February: Print Delivery
Open House brochure | December: Kick off meeting / discuss successes/ issues of last year; January: PDFs to contributors 2nd proofs out Sign off from contributors; February: Final sign off from stakeholders; March: Print Delivery
Arrival Guide | December: Kick off meeting Design concepts; January: Copyediting Proofing; February: Proofing Sign off Print; March: Print Delivery
UCAS Entry requirements guide | January: Export report from Campus Solution and format; February: Student Recruitment sign off / Print / Delivery
Postgraduate Prospectus | February: Kick off meeting / discuss successes/ issues of last year; March: Contributors to edit; April: Text editing and proofing process Design concepts; May: PDFs to contributors 2nd proofs out Sign off from contributors; June: Final sign off from stakeholders; July: Print Delivery
International Undergraduate Prospectus | February: Kick off meeting / discuss successes/ issues of last year; March: Contributors to edit, Design concepts; April: Text editing and proofing process, PDFs to contributors 2nd proofs out, Sign off from contributors; June: Final sign off from stakeholders; July: Print Delivery
Armitage fitness campaign (Summer) | March: Design ideas / production schedule / photography; April: PDFs to contributors / Final sign off from stakeholders; May: Print Delivery
What's On Guide (preview/1st edition) | March: Kick off meeting / discuss successes/ issues of last year; April: Text editing and proofing process Design concepts; May: Text editing and proofing process Design concepts; June: Print Delivery
Welcome events | March: Discuss with Karen and wider Welcome Group Start to book rooms; April: Book necessary companies; May: Continued organisation/ booking Feed into What's on guide; June: Continued organisation/ booking; July: Continued organisation/ booking Feed into 2nd edition; August: Last-minute organisation
Orientation Guide | April: Kick off meeting / discuss successes/ issues of last year; May: Text editing and proofing process Design concepts; June: Text editing and proofing process Design concepts; July: Print Delivery
Welcome video | April: Kick off meeting / discuss ideas / set schedule; May: Production; June: Production; July: Sign-off
Confirmation & Clearing website | April: Kick off meeting / discuss successes/ issues of last year; May: Development; June: Development; July: Sign-off
Welcome website | April: Kick off meeting / discuss ideas / set schedule; May: Development; June: Development; July: Development; August: Sign off
What's On Guide (full/2nd edition) | May: Kick off meeting / discuss successes/ issues of last year; June: Text editing and proofing process; July: Design concepts Print; August: Print Delivery
Study abroad guide | May: Kick off meeting / discuss successes/ issues of last year; June: Text editing and proofing process; July: Design concepts Print; August: Print Delivery
Ask Me Coordination | May: Kick off meeting / discuss successes/ issues of last year; June: Student Ambassador recruitment / produce guide for staff and order badges and lanyards; July: Identify and allocate roles / order uniform and signage / print guide / staff distribution lists; August: Finalise rotas / communicate troles / develop training plan
Ask me guide for staff | May: Kick off meeting / discuss successes/ issues of last year; June: Text editing and proofing process; July: Design concepts Print; August: Print Delivery
Sport & Active Lifestyles Guide | May: Kick off meeting / discuss successes/ issues of last year; June: Text editing and proofing process Design concepts; July: PDFs to contributors / Final sign off from stakeholders; August: Print Delivery
Armitage fitness campaign (Welcome) | May: Kick off meeting / discuss successes/ establish needs . Budget; June: Design ideas / production schedule / photography; July: PDFs to contributors / Final sign off from stakeholders; August: Print Delivery
Student bloggers | May: Start discussions about recruitment; June: Agree budgets and process with SRID; July: Start recruitment process; August: Hire bloggers
E-advantage newsletter | Issue 10 | Review | Implmentation of review | Issue 1 | Issue 2 | Issue 3 | Issue 4 | Issue 5 | Issue 6 | Issue 7 | Issue 8 | Issue 9
Other videos | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing
External website listings | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing
Social media monitoring and evaluation | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing
Admissions Twitter & Facebook | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing