## Work Plan
Code | Task | Duration | Start Date | Due Date | Days Until Due | Status | Responsible | Deliverable | 2014-04-11 | 2014-04-18 | 2014-04-25 | 2014-05-02 | 2014-05-09 | 2014-05-16 | 2014-05-23 | 2014-05-30 | 2014-06-06 | 2014-06-13 | 2014-06-20 | 2014-06-27 | 2014-07-04 | 2014-07-11 | 2014-07-18 | 2014-07-25 | 2014-08-01 | 2014-08-08 | 2014-08-15 | 2014-08-22 | 2014-08-29 | 2014-09-05 | 2014-09-12
Project Initiation
INIT001 | Write Project Initiation Document | 5 days | 2014-03-28 | 2014-04-01 | Done | Complete | J Bloggs | bar: 2014-04-11
INIT002 | Produce Project Charter | 1 day | 2014-03-31 | 2014-03-31 | Done | Complete | J Smith | bar: 2014-04-11
INIT003 | Write detailed project plan | 5 days | 2014-04-11 | 2014-04-15 | Done | Complete | J Bloggs | bar: 2014-04-11
INIT004 | Identify initial risks, issues and actions and establish logs | 5 days | 2014-04-11 | 2014-04-15 | Done | Complete | J Smith | bar: 2014-04-11
INIT005 | Issue and Risk management process created and communicated | 1 day | 2014-04-21 | 2014-04-21 | Done | Complete | J Smith | bar: 2014-04-18
INIT006 | Document project deliverables | 1 day | 2014-04-18 | 2014-04-18 | Done | Complete | J Smith | bar: 2014-04-18
INIT007 | Map stakeholders | 1 day | 2014-04-18 | 2014-04-18 | Done | Complete | B Jones | bar: 2014-04-18
INIT008 | Weekly project team meetings set up | 1 day | 2014-04-18 | 2014-04-18 | Done | Complete | J Smith | bar: 2014-04-18
INIT009 | Run weekly team meetings and fortnightly project reporting | Whole Project | 2014-05-02 | 2014-09-12 | 154 | In Progress | J Smith | bar: 2014-05-02 to 2014-09-12
INIT010 | Produce Status Report template | 1 day | 2014-04-18 | 2014-04-18 | Done | Complete | J Bloggs | bar: 2014-04-18
INIT011 | Finalise and publish fortnightly status reporting process/schedule | 1 day | 2014-04-21 | 2014-04-21 | Done | Complete | J Smith | bar: 2014-04-18
INIT012 | Steering committee defined and scheduled | 5 days | 2014-04-18 | 2014-04-22 | Done | Complete | B Jones | bar: 2014-04-18
INIT013 | Track and report benefits realisation | 1 day | 2014-05-16 | 2014-05-16 | Done | Complete | B Jones | bar: 2014-05-16
INIT014 | Project Initiation Meeting | 1 day | 2014-04-20 | 2014-04-20 | Done | Complete | J Smith | bar: 2014-04-18
INIT015 | Sign-off PID and related documentation | 1 day | 2014-05-06 | 2014-05-06 | 25 | In Progress | A Roberts | ü | bar: 2014-05-02
INIT016 | Sign-off project plan with Project Sponsor | 1 day | 2014-05-06 | 2014-05-06 | 25 | In Progress | A Roberts | ü | bar: 2014-05-02
Communications
COM001 | Write communications plan | 4 days | 2014-05-09 | 2014-05-12 | Done | Complete | J Smith | bar: 2014-05-09
COM002 | Sign-off communications plan with Project Sponsor | 1 day | 2014-05-20 | 2014-05-20 | Done | Complete | B Jones | ü | bar: 2014-05-16
COM003 | Develop Engagement Tracker | 4 days | 2014-05-09 | 2014-05-12 | Done | Complete | J Smith | bar: 2014-05-09
COM003 | Deliver communications plan | Whole Project | 2014-05-16 | 2014-09-12 | 154 | In Progress | B Jones | bar: 2014-05-16 to 2014-09-12
COM004 | Use Engagement Tracker to monitor project preparedness | Whole Project | 2014-05-16 | 2014-09-12 | 154 | In Progress | B Jones | bar: 2014-05-16 to 2014-09-12
Training
TR001 | Write training plan | 4 days | 2014-06-27 | 2014-06-30 | 80 | In Progress | R Patel | bar: 2014-06-27
TR002 | Write new procedure guides and training materials | 30 days | 2014-07-04 | 2014-08-05 | 116 | Not started | R Patel | bar: 2014-07-04 to 2014-08-01
TR003 | Review training materials and plans for future training | 3 days | 2014-08-08 | 2014-08-10 | 121 | Not started | R Patel | bar: 2014-08-08
TR004 | Sign off training materials | 1 day | 2014-08-12 | 2014-08-12 | 123 | Not started | R Patel | ü | bar: 2014-08-08
TR005 | Deliver overview training to Project Team | 1 day | 2014-06-27 | 2014-06-27 | 77 | Not started | R Patel | bar: 2014-06-27
TR006 | Deliver training to users | 1 day | 2014-08-22 | 2014-08-22 | 133 | Not started | R Patel | bar: 2014-08-22
Go Live
LIVE001 | Execute cutover plan | 10 days | 2014-09-05 | 2014-09-05 | 147 | Not started | B Jones | bar: 2014-09-05
LIVE002 | Go Live | 1 day | 2014-09-12 | 2014-09-12 | 154 | Not started | B Jones | bar: 2014-09-12
LIVE003 | Post go-live support | 15 days | 2014-09-13 | 2014-09-30 | 172 | Not started | B Jones
LIVE004 | Benefits Realisation Analysis | 4 days | 2014-12-12 | 2014-12-15 | 248 | Not started | B Jones
LIVE005 | Wrap up meeting and lessons learned | 1 day | 2014-12-15 | 2014-12-15 | 248 | Not started | B Jones | P
|  | Today's Date | 2014-04-11