Abbreviations:  JER (Jill Roberts)   MH - Miranda Hall  PO (Peter Ogilvie)  RT (Rob Tempelman)  M Ho (Mandy Ho)  LB (Louise Bissell) GM (Gemma Mossop)  EY (Enrst and Young – Auditors)  JD (Jess Dodd)  AP (Accounts Payable)  MB (Michelle Bailey  CT (Chris Trask) )  PP (Pam Plested)  JT (Julie Thomson)  MK (Design team)   JC (Janette Carter)  LBr (Lisa Bracken)  LM (Lucia McCaddon)

| Month | Mon | Tue | Wed | Thu | Fri |
| --- | --- | --- | --- | --- | --- |
| Dec 2018 | 31 | 1 | 2 | 3 | 4 |
| Jan 2019 | 7 EY Planning Audit Commences (2 weeks) | 8 | 9 | 10 | 11 |
|  | 14 | 15 | 16 | 17 | 18 EY Planning Audit Completes |
|  | 21 | 22 | 23 | 24 | 25 |
|  | 28 | 29 | 30 | 31 | 1 |
| Feb 2019 | 4 | 5 | 6 | 7 | 8 |
|  | 11 | 12 | 13 | 14 | 15 |
|  | 18 EY to confirm PBC requirements for IT audit | 19 | 20 | 21 | 22 |
|  | 25 Preparation of pension reports (PO) this week (end of February)- practice for year end | 26 | 27 | 28 | 1 - Pension reports to GM (PO) to end of February for review |
| Mar 2019 | 4 | 5 | 6 | 7 | 8 |
|  | 11 | 12 | 13 | 14 | 15 |
|  | 18 | 19 | 20 | 21 | 22 |
|  | 25 Data extracts for GL journal to EY – PH (to February period) Trial balances to February period to EY (JER) | 26 | 27 | 28 | 29 |
| Apr 2019 | 1 Template rolled forward for accounts preparation (JER) | 2 | 3 | 4 | 5 |
|  | 8 EY Interim (1) Audit Commences (2 weeks) Draft PBC list available | 9 | 10 | 11 | 12 Audit PBC list available with identified owners of deliverables (JER) |
|  | 15 EY to confirm data extract requirements and scripts (including payroll) Subs Financial statements submissions issued (JER) | 16 | 17 | 18 EY Interim (1) Audit Completed | 19 Good Friday |
|  | 22 Bank holiday | 23 | 24 | 25 | 26 |
|  | 29 | 30 | 1 | 2 | 3 Leased asset register circulated (M Ho) |
| May 2019 | 6 Bank holiday | 7 | 8 Consider and plan format changes to Financial Review front and KPI’s section (MH) Reminder re capital commitments sent out (JD) | 9 | 10 |
|  | 13 - Interim outturn review meeting this week (JER) | 14 CP to be completed by Subs (For April month end YTD actuals) | 15 | 16 Statutory accounts template for consolidation to be submitted to centre (Subs) to April Month end | 17 |
|  | 20 - Accounting Policies front section reviewed to assess required changes (JER) | 21 Subs Financial statements submissions reconcilied to CP (LBr). Anomalies and differences identified and investigated. (LB) | 22 - Accounting policies finalized (JER) | 23 | 24 Faculty and Shared Services forecasts due - Eliminations financial statements template sumitted to JER - Eliminiations Financial statements submission reconcilied to CP (LBr). Anomalies and differences identified and investigated. (LBr) |
|  | 27 Bank holiday | 28 Supplementary financial statements information templates circulated to area specialists (JER) | 29 | 30 - Statutory adjustment of postings on 4231 (PO) - Pension reports to GM (PO) for interim year end | 31 - 3pm (after subledger close) GRNI accrual including capital (PO) - Tuition fee deferral (RT) - Investment property adjustments (JD) |
| Jun 2019 | 3 - PA-GL rec (PO) - SOF corrections (Before 3 pm) - Commissioned assets adjustments - (before 10am) Capital leads - Capital income recognition journals (10-12pm) – M Ho - Capital Income recognition adjustments (before noon) Capital leads - Central Income recognition adjustment (zeroing) – (between noon and 3 PM) (PO) - Depreciation postings noon-5pm (JD) - 5 pm Ledger close (except for restricted reserves and split credits) | 4 - Split credits posted (period 10) - JT - Restricted reserves adjustment posted - JER - Commence management accounts | 5 - Review of static balances and unexpected signage to be sent out - PO - Uncommissioned assets review/ confirmation reminder sent (M Ho) - Asset Verifications Exercise lists sent out (M Ho) - FSR tables circulated for variance review (faculties) - p10 (LM) - FSR tables and anomalies investigated (System group leads) - p10 - Projects balances report and GL summary to auditors for sampling (JER) - Shared Services management accounts due - Faculty and PSS/GUO management accounts due - Subs to send supplier statements to UoM | 6 - Library open access data to RT(C Riches) - Run OF data analytics extract for E&Y pds 1-10 (Phil Hornby) - Consolidation of University management accounts and forecast (Continued) - Management accounts and Forecast to FSC (MH) - Subsidiary company intercompany recs completed (AP) (send to LBr when complete) | 7 |
|  | 10 - Test process for Library Open access journal RT - Leased asset register completed & returned (all) - Capital commitments notified to Jess Dodd (all) - Samples required for interim audit received back from auditors - e.g. grants (E&Y) - Uncommissioned assets review/ confirmation completed (capital leads) - Distribute potential movements on restricted reserves P10 (JER) - Preparation interim Financial Statements (period 10) this week (including subs). Staff numbers and bandings not required for interim. - Consolidation of interim Financial Statements commences (Subs) | 11 - Commentary in the Notes to the accounts format (interim) circulated (RT) - Finance Sub committee | 12 | 13 - Rec of payments to the pension schemes (LB) | 14 |
|  | 17 - Systems leads to feedback to HoFFRA and LM that FSR figures have been reviewed in faculty and anomalies corrected - Leased asset register re-circulated (M Ho) - Reminder re donated asset forms and disposals (M Ho) - Completion of supplementary financial statements information (per circulated template) - area specialists - Payroll data for FS from payroll | 18 - Agree the terms of the actuary’s engagement for the year and set a date for discussions in early July around proposed assumptions (LB) - Asset Verifications Exercise (return of signed asset verification forms by HoFF including any amendments) - HoFFs | 19 | 20 - Commentary in the Notes to the accounts format (interim) review completed - Capital information prepared to inform cash flow statement (JD) | 21 |
|  | 24 - Signoff of commentary in Notes to the accounts format (interim) – HoFFRAs. Confirming email to Jill Roberts - JER to notify note owners that Commentary in Notes to the accounts format available - All notes completed – interim Financial Statements - Consolidation completed - interim Financial Statements | 25 - ‘Note owners’ start review of notes and commentary - Cashflow commenced (GM) | 26 - Review HESA guidelines for any changes and communicate/discuss as needed - LM | 27 Cashflow completed for interim Financial Statements (GM) | 28 - Review of cashflow statement (LB) |
| Jul 2019 | 1 - ‘Note owners’ complete review of notes and commentary - Final completion of Consolidated Financial statements for review (JER) | 2 - Review of static balances and unexpected signage to be sent out – PO - Detailed timetable for final audit to be agreed (meetings arranged etc.) (EY and JER) | 3 FSR tables prepared (TBC) and anomalies identified - p11 Review of interim Financial Statements (LB) | 4 - FSR tables circulated for variance review (systems working group) - p11 - Conference call with the UMSS actuaries (LB) - Preparation for USS deficit calculation – consider all assumptions (LB) | 5 - Board of Governor and SLT lists for current year to JER (M Rollinson) - Officers and advisers information (to JER (Mark Rollinson) - P11 fixed asset register and confirmation forms sent out (M Ho) |
|  | 8 - Distribute potential movements on restricted reserves P11 (JER) - Board of Governor and SLT lists for year to Payroll for trustee expenses note HR and to Treasury for FTCC claimed expenses. (JER) | 9 - Draft IT audit report available (E&Y) for comment by Finance and IT - Identify all changes to FSR reporting for current year end (LM) - Gathering data for investment properties valuation (JD) | 10 | 11 - Reminder re clearing, deferring, accruing OfS balances (M Ho) - Review of interim Financial Stataments (CT) - Draft investments financial statements note based on 30 June data for roll forward at year end (GM) | 12 |
|  | 15 - All areas undergoing Organisation changes to confirm to PO - PA-GL rec (PO) - Petty cash floats circulated (Income Office) - Interim and IT management letter to be available (EY) | 16 - Subs roll-forward of templates with prior year comparatives to be completed (Jo Rodger) - Interim audit close meeting (to include IT findings) - Board of Governor and SLT lists for current year to masterdata team to identify party numbers (JER) | 17 | 18 Review all changes to FSR reporting for current year end (LM) | 19 - CFTA available from Roger Starling - Circulate to HoFFRAs for review (M - Systems working group leads to feedback to HoFFRA and LM that FSR figures have been reviewed in faculty and anomalies corrected |
|  | 22 - Reminder re capital commitments sent out (JD) - Last day for donated asset and disposal forms to be returned to M Ho (HoFFS and HOFFRAS) - Request holiday records from IT and FSE (LM) - Board of Governors responsibilities section of Financial Statements prepared – (LB) | 23 - PA-GL rec (PO) - Petty cash floats reimbursed to income office (all petty cash holders) - All adjustments from P11 Jun 15 fixed asset register posted (capital leads) - Fixed asset confirmation forms to be returned to M Ho (HoFFS) - Board of Governor and SLT lists for current year with party numbers to JER - PP | 24 - Send out 403 report for review of activity code set up and flags (helpdesk) - Send out Allocations report ( to end of July) - PO - Incomplete PO's to be run daily in the last week - Last date for sundry payments - HoFFRAs confirm CFTA to M Ho - Last date for intercompany transactions (all) | 25 - Last day for requesting new customer accounts and new supplier accounts (all) - Last load from Kinetix into Oracle (Sys admin) - Key Travel upload posted (AP) - Last BACS payment run to suppliers | 26 - Last payroll for year processed and passed through to Oracle (HR) - Detailed bal sht report available including suspense - to end of July (JER) - Request SSC not to process any further tuition fee adjustments if possible until 1st August (helpdesk) |
|  | 29 - Payroll posted and reports sent out (helpdesk) - Circulate Project balances report (PO) - PA-GL rec (PO) - Bulk cash/cheques submitted to IO for guarnateed posting - Purchasing cards charges posted (treasury) - Statutory adjustment of postings on 4231 (PO) after CS interface | 30 - Tuition fee deferral (PO) - Payroll posting errors cleared (faculties) - Payroll rec completed (PO) and queries distributed - Last requisitions (2pm), last approvals of requisitions (5pm) - Post CFTA (M Ho) - Confirmation that OfS accounts cleared and supporting documents returned to M Ho before 12 noon (Faculties) | 31 - Schedule Project balances report for year end version (PO) - Save PA-GL rec for year end (PO) - 12 noon - last time for processing AR invoices, AP invoices, converting and issing PO's, receipting, invoice holds - Month end close (12 noon) - Stocktakes (except MUP) - Open next encumbrance year (JER) - Accruals reports for RBS cards available and posted (treasury) - Send out projects overheads and allocations report ( to end of July) after subledger close - helpdesk - OfS grnt income checked and reconciled (M Ho) - GRNI accrual including capital (PO) - after ledger close - Pension choice adjustment workings available (PO) - Schedule of all pension payments made in year available to LB (PO) | 1 - Uncommissioned assets reviewed and all moved to commissioned codes if required before 5pm (Capital leads) - No capital postings after 5pm - UKRPIF adjustment for chaity codes posted (AB) - Detailed bal sht report available including suspense (JER) - RBS cards reports available - failed codes (procurement) - Adjustments for grossing up of Trade debtors and creditors posted (Treasury) - Euro-Coordinator bank account adjustment posted (PP) - Project balances report extracted - from 31st (PO) - Suspense accounts checked and cleared (all) - Stock adjustment posted (faculties) - Treasury adjustments posted (euroordinators and grossing up of Tr Dr and Crs) - MB - Payroll Reports available - 2000 codes (DM) - All manual accruals posted (all areas) - Circulate allocations imbalances (PO) - Post opening encumbrance balance journal (M Gilmore/JER) - FSE post stock journals - Research provision adjustments finalised (HoFRF) - Source of funds corrections | 2 - Capital income recognition journals before 10.30 am – Capital leads - Capital income recognition reconciliation before 12 noon (M Ho) - Depreciation postings 5pm (M Ho) - Central accrual deferral of matched income (PO) - 12 noon (after income recognition) - Prepare P2P and AP KPIs (PO) - Clear all allocations imbalances (all areas) - Post Holiday pay accrual (LM) - Final adjustments (other than matched and capital codes) - Timetable call to actuaries to finalise assumptions with UMSS and then notification to GMPF (LB) - Review of static balances and unexpected signage to be sent out (after zeroing) – PO |
| Aug 2019 | 5 - Commence school and faculty management accounts (all) - Send out P2P and AP KPIs (PO) - Cut-off reports distributed - PO - Check that all bank recs agree to balance sheet cash balances (PP) - Capital cost, dpn and income reconciliations completed (M Ho) - Send out the list of assets requiring physical verification (M Ho) - Post movements on restricted reserves P12 (JER) - non capital - Write off any residual allocation imbalances (PO) - Library open access data to RT (C Riches) - Subs to send supplier statements to UoM | 6 - Library Open access journal posted (JER) - Post movements on restricted reserves (capital related) P12 (JD) - OfS rec reviewed (JC) - Detailed bal sht report available including suspense (JER) - Finalise USS deficit calculation and check contributions reconcile to UoM records (LB) - Finalise investment property valuation (JD) - Final postings to any endowment accounts (faculties) - Close general ledger (soft close) – JER - Send UMSS cash flows to actuary (LB) - Subsidiary company intercompany recs completed (AP) (send to LBr when complete) - Capital cost, depreciation and income reconciliations reviewed (JD) | 7 - Payroll rec checked (PO) and updated - Allocations checked (PO) - Detailed bal sht report available including suspense (JER) - Check all Accruals journals have reversed (all) - Shared services management accounts end of day - Review HESA guidelines for any late changes and communicate/discuss as needed - LM - FSR tables circulated for variance review (TBC) - p12 - Save suspense accounts recs to G drive (all) - Central endowment adjustments posted (JC) - Split credits posted (JT) | 8 - All suspense account reconciliations to be saved to the G drive as directed (all) - FSR tables anomalies investigated (Systems working group) - p12 - Faculties to submit their consolidated management accounts (HoFFRAS) - Cash and Cash equivalants breakdown provided re cash flow to GM (M Bailey) - Meeting to review projected outturn (JER) - Sales and purchase ledger lists showing year end position and turnover by suppler to JER (AP and AR) | 9 - Check all suspense account recs saved (PO) - ROI lists for BoG to JER (Mark Rollinson) - Extract ROI lists for members of staff for related parties note (JER) |
|  | 12 - Leased asset register completed (all) - Capital commitments notified to JD (all) Market value adjustment for July posted (JC) | 13 - Physical Verifications completed (Capital leads) and returned to M Ho - Systems leads to feedback to HoFFRA and LM that FSR figures have been reviewed in faculty and anomalies corrected - Final subs uploads into CP (based on Actuals for month 12) completed - Hard close (Oracle) excl pension - JER - Send UMSS asset values to actuary (after checking with Mercers) (LB) | 14 - Final checks following close (JER) - Preparation of financial statements notes this week (see separate list) - Financial Statements preparation commences (JER) - Financial Statements Subs entry into CP templates - Consolidation commenced (JC) | 15 - TB extracts run and finalised (JER) - Staff numbers, and bandings to JER (Jacqui Brynning) - Excellence awards, SMT remuneration, board expenses and President's remuneration to JER (Jaqui Bryning) - Board of Governor and SLT expenses for FTCC transactions to JER (PP) - Commentary in the Notes to the accounts format prepared and circulated (UoM only excl pension) (RT) - Receipt of FRS 102 actuarial values (LB) - Subs financial statements upload sheets completed and submitted to Centre (SUBS) | 16 - FSR preparation commenced (JC) - Research report to auditors (JER) - Reconcile UMSS cash flows to UoM and subs records / proposed disclosures (LB) - LB to prepare pension journals ready for review |
|  | 19 - Completion of supplementary financial statements information (per circulated template) - area specialists - Subs submissions reconciled to CP uploads and differences identified and investigated (LBr) - Audit Commences (subsidiaries and transactional) - Review of pension journals (JC and JRodger) - Pension notes commentaries and disclosures (LB) | 20 - Individual Financial Statements preparation commences for subs accounts - SUBS (Lynda Connolly and Carol Feely) - Audit Commences – transactional areas (University) - Eliinations submissions reconciled to CP uploads and differences identified and investigated (LBr) - Consolidation commenced (JER) - Final date for posting of pension adjustments (LB) - Tracker Commenced (JER) | 21 - Management accounts finalised (JC) and reviewed by CT - All Financial Statements notes to be completed (separate list) - Final Research sample received back from auditors (E&Y) - Commentary in the Notes to the accounts format completed - Data analytics extract for E&Y pds 11-12 (Phil Hornby) | 22 - Management accounts to Director of Finance for review (CT) - Commentary in Notes to the accounts format signoff – HOFFRAs (email Jill Roberts) - Eliminations financial statements upload sheets completed on CP (LBr) | 23 - Draft Interim audit report available (if required) (E&Y) - Financial Statements Consolidation completed (JER) - JER to notify note owners that Commentary in Notes to the accounts format available - JER to share consolidated financial statements with note owners - Note owners’ start review of notes and commentary |
|  | 26 Bank holiday | 27 - Submit complete list of Wellcome grants to payroll (Jacqui Bryning) so that checks can be made to ensure all new staff in prior year have signed employment contracts (Alison Bate) - Audit Commences – all areas (University) | 28 - Details of all organisational changes to PO and JER [child codes from where to where] - Note owners’ complete review of notes and commentary - Review of eliminations (LB) | 29 - Consolidated Financial Statements to reviewers excl cash flow and pension note (MH, other nominated reviewers) - PO - confirm all management accounts completed and commence org changes (parent and child codes) - Key UOM notes available for auditors (fixed assets, debtors, creditors, Income and expenditure) (JER, JD) - Cashflow to be completed (GM) - Pension notes to be completed (GM) | 30 - Accounts review completed and feedback to FC (MH, other nominated reviewers) - Subs financial statement scompleted |
| Sep 2019 | 2 - Month end close and month end journals Amendments to accounts completed following reviews – JER - Subs Final close meetings this week | 3 - FSR research income analysis to Lita Denny JER) - Papers available for Audit Committee (front sections) - Review of front sections (except Financial review and Review of the year) - CT - Commence work on Financial Review and KPIs (MH) | 4 - LB accounts and front sections review | 5 - Accounts updated following LB accounts review (am) - Accounts updated following LB accounts review (JER) | 6 - CT accounts and front sections review |
|  | 9 - Accounts updated following CT accounts review (JER) - Papers available for Audit Committee (interim audit report and IT audit report) E&Y - PO - All org changes completed on Oracle and CP. | 10 - Accounts to DoF for review – JER - Final amendments to FS following DoF review (JER) | 11 Consolidated Financial Statements to Auditors (JER) | 12 | 13 Finalise Financial Review and KPIs (MH) |
|  | 16 - Review Financial Review and KPIs (CT) - Backloading completed for prior year actuals (PO) | 17 | 18 | 19 | 20 - Financial review finalised (DoF) and provided to auditors |
|  | 23 - All subsidiaries final Financial Statements from auditors to LB (EY) | 24 | 25 | 26 | 27 - On site audit work completed (E&Y) |
|  | 30 | 1 | 2 | 3 - E&Y technical reviews completed and feedback provided | 4 |
| Oct 2019 | 7 - Chair’s Foreword available (Neil Condron) | 8 | 9 - Draft Audit Report available (E&Y) | 10 - Draft management letter available for review (EY) - Points from EY technical review actioned and cleared (JER) - President’s Review of the Year finalized (Neil Condron) - Later front sections to be provided to EY (Review of the year, Chair’s foreword, Year in pictures) - Going concern paper to be completed (Gemma Mossop) | 11 |
|  | 14 - Audit close meeting this week - Final proof read of accounts before submission to FSC (LB) - Final review of later front sections (Finance review and Review of the Year) - CT | 15 | 16 - Responses to management letter written (Jill Roberts) | 17 | 18 |
|  | 21 - E&Y technical reviews completed and feedback provided for later front sections (Review of the year, Chair’s foreword, Year in pictures) | 22 | 23 | 24 | 25 |
|  | 28 - Review of final PDF proofs (CT) | 29 | 30 | 31 | 1 |
| Nov 2019 | 4 Papers available for Finance and Audit Committee | 5 | 6 | 7 | 8 |
|  | 11 | 12 | 13 Finance Committee Audit Committee (Joint meeting) | 14 | 15 |
|  | 18 | 19 | 20 Board of Governors | 21 | 22 |
|  | 25 | 26 | 27 | 28 | 29 |
| Dec 2019 | 2 | 3 | 4 | 5 | 6 |
|  | 9 | 10 | 11 | 12 | 13 |
|  | 16 | 17 | 18 | 19 | 20 |
|  | 23 | 24 | 25 | 26 | 27 |
|  | 30 | 31 | 1 | 2 | 3 |

More Calendar Templates: 2019, 2020, Online Calendar

Created with WinCalendar Calendar Creator