## Sheet1
| September | October | November | December | January | February | March | April | May | June | July | August
Undergraduate Pocket Guide | September: Kick off meeting / discuss successes/ issues of last year; October: Text editing and proofing process Design concepts; November: Course listings from WPM proofing (taken from updates schools do for prospectus); December: Final sign off from stakeholders; January: Print Delivery
UCAS Entry requirements guide | October: Schools asked to update A level and IB entry requirements on WPM Design concepts; November: Deadline for A level and IB entry requirements; December: Schools asked to update addional entry requirements on WPM 1st design proofs; January: Early Jan deadline for additional entry requirements All WPM information updated SC&M export from Campus Solution; February: Student Recruitment sign off / Print / Delivery
Open House brochure | December: Kick off meeting / discuss successes/ issues of last year; January: PDFs to contributors 2nd proofs out Sign off from contributors; February: Final sign off from stakeholders; March: Print Delivery
Arrival Guide | December: Kick off meeting Design concepts; January: Copyediting Proofing; February: Proofing Sign off Print; March: Print Delivery
Good luck postcard | January: Brainstorm ideas, design concepts; February: Proofing Data gathering; March: Print and distribution
Postgraduate Prospectus | February: Kick off meeting / discussions re format; March: Upload to Sharepoint for updating by Schools and teams; April: Text editing and proofing process Design concepts; May: PDFs to contributors Schools update course info on WPM; June: Final sign off from stakeholders; July: Print Delivery
What's On Guide (preview/1st edition) | March: Kick off meeting / discuss successes/ issues of last year; April: Text editing and proofing process Design concepts; May: Proofing process; June: Print Delivery
Get Ready Guide | March: Kick off meeting / discuss successes/ issues of last year; April: Text editing and proofing process Design concepts; May: Proofing process; June: Print Delivery
Welcome video | April: Kick off meeting / discuss ideas / set schedule; May: Production; June: Production; July: Sign-off
Confirmation & Clearing website | April: Kick off meeting / discuss successes/ issues of last year; May: Development; June: Development; July: Sign-off
Welcome website | April: Kick off meeting / discuss ideas / set schedule; May: Development; June: Development; July: Development; August: Sign off
Undergraduate Prospectus | Deadline for Schools and teams for course detail copy | Schools asked to update A level and IB entry requirements on WPM Design concepts | Deadline for A level and IB entry requirements | Schools asked to update additional entry requirements on WPM 1st design proofs | Early Jan deadline for additional entry requirements All WPM information updated ready for course profiles rollover Late Jan final sign off from stakeholders | Print Delivery |  | Kick off meeting / discuss successes/ issues of last year | Upload to Sharepoint for updating by Schools and teams | Updating by Schools and teams | Updating by Schools and teams | Updating by Schools and teams
International Undergraduate Prospectus | Deadline for Schools and teams for course detail copy | Schools asked to update A level and IB entry requirements on WPM Design concepts | Deadline for A level and IB entry requirements | Schools asked to update additional entry requirements on WPM 1st design proofs | Early Jan deadline for additional entry requirements All WPM information updated ready for course profiles rollover Late Jan final sign off from stakeholders | Print Delivery |  | Kick off meeting / discuss successes/ issues of last year | Upload to Sharepoint for updating by Schools and teams | Updating by Schools and teams | Updating by Schools and teams | Updating by Schools and teams
Living in Manchester | September: Print, delivery; May: Kick off meeting / discuss successes/ issues of last year; June: Contributors to edit, sort out profiles and photography; July: Text editing and proofing process Design concepts; August: PDFs to contributors 2nd proofs out Sign off from contributors & stakeholders
International Advantage | September: Print, delivery; May: Kick off meeting / discuss successes/ issues of last year; June: Contributors to edit, sort out profiles and photography; July: Text editing and proofing process Design concepts; August: PDFs to contributors 2nd proofs out Sign off from contributors & stakeholders
Home Advantage | September: Print, delivery; May: Kick off meeting / scoping of project; June: Contributors to edit, sort out profiles and photography; July: Text editing and proofing process Design concepts; August: PDFs to contributors 2nd proofs out Sign off from contributors & stakeholders
Ask me for staff comms plan | May: Kick off meeting / discuss successes/ issues of last year; June: Text editing Consultation; July: Text editing Consultation; August: Implementation
Student bloggers | May: Start discussions about recruitment; June: Agree budgets and process with SRID; July: Start recruitment process; August: Hire bloggers
Offer letter leaflet | June: Discussions around target audience and format; July: Copy and design; August: Sign off and print
What's On Guide (full/2nd edition) | September: Print, delivery; July: Design concepts Print; August: Print Delivery
Student profile projects | Recruitment process | Interviewing | Filming | Recruitment process | Interviewing | Filming | Recruitment process | Interviewing | Filming | Recruitment process | Interviewing | Filming
E-advantage newsletter | Issue 10 | Review | Implementation of review | Issue 1 | Issue 2 | Issue 3 | Issue 4 | Issue 5 | Issue 6 | Issue 7 | Issue 8 | Issue 9
Key
SC&M projects (some input required by other teams)
Projects with input required from Schools