Implementation Plan: Framework for the Development, Approval, Implementation, Monitoring and Review of Institutional Policy and Procedure (GET)

X   = responsibility for task/ significant involvement

GET = Graduate Education Team

ADs = Associate Deans of Faculty

MDC = Manchester Doctoral College committee (ADs/ AVP/ Director of RBESS/ Dr. SRID/ PGR reps/ UNION reps)

HOS/ HOSA = Head of School/ Head of School Admin

Dn/ DoFO = Deans of Faculty/ Director of Faculty Operations

GAG = Graduate Administrators Group (Heads of Faculty PGR Admin)

WG = Working Group

| Stage 1: Policy Development |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Tasks to be delivered | GET | ADs | MDC | HOS/HOSA | DN/ DoFO | GAG | WG |
| Policy/ procedural development need confirmed | X |  |  |  |  | X |  |
| Consider objectives of the WG/ GAG, leading to a plan of work and initial recommendations | X |  |  |  |  | X | X |
| Any good practice to be identified | X |  |  |  |  | X | X |
| Agree initial recommendations | X | X |  |  |  | X |  |

| Stage 2: Consultation |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Tasks to be delivered | GET | ADs | MDC | HOS/HOSA | DN/ DoFO | GAG | WG |
| Manage Stakeholder consultation | X |  |  |  |  |  |  |
| Redrafted policy, (with any relevant summary report, framework or flow chart) to be emailed to all stakeholders for comment | X | X | X |  |  |  |  |
| Policy sent for open consultation via intranet pages | X |  |  |  |  | X |  |
| Comments collated for MDC/ GAG for consideration and approval. | X |  | X |  |  | X |  |
| Develop final draft of policy for approval at Senate | X |  |  |  |  |  |  |

| Stage 3: Policy Approval |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Tasks to be delivered | GET | ADs | MDC | HOS/HOSA | DN/ DoFO | GAG | WG |
| Approval by GAG. | X |  |  |  |  | X |  |
| Approval by MDC. | X |  | X |  |  |  |  |
| Approval by SENATE | X |  |  |  |  |  |  |

| Stage 4: Policy Implementation |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Tasks to be delivered | GET | ADs | MDC | HOS/HOSA | DN/ DoFO | GAG | WG |
| Oversee Implementation at institutional level. | X |  |  |  |  |  |  |
| Send email to Schools; cc Faculty PSS to indicate expectations as per the implementation plan. | X |  |  |  |  | X |  |
| Ensure consistent implementation at School level & disseminate responsibilities of all staff with regards implementation and consequences of non compliance. | X |  |  | X |  | X |  |

| Stage 5: Monitoring and Review |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Tasks to be delivered | GET | ADs | MDC | HOS/HOSA | DN/ DoFO | GAG | WG |
| Embed the annual review of any new policies in the cycle of annual monitoring of programmes and Periodic review. | X |  |  |  |  |  |  |
| Maintain an oversight of the appropriateness of existing policies and monitor the effectiveness of new policies via management groups. Set up reviews as required. | X |  |  |  |  |  |  |

| Stage 6: Evaluation |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Tasks to be delivered | GET | ADs | MDC | HOS/HOSA | DN/ DoFO | GAG | WG |
| Conduct a review of the effectiveness of the implementation of the Policy after 6 and 12 months. To include stakeholder feedback | X | X | X | X | X | X | X |