## Sheet1
Calendar of Student Communications and Marketing pre-registration work 2016-17
| September | October | November | December | January | February | March | April | May | June | July | August
Conversion publication review and planning | Plan survey re Arrival Guide, Get Ready and What's On | Send Survey | Assess survey feedback Make decisions on next cycle | Implement in publications |  |  | Plan survey re My Manchester, Offer letter leaflet | Send Survey | Assess survey feedback Make decisions on next cycle | Implement in publications
Undergraduate Pocket Guide | September: Kick off meeting / discuss successes/ issues of last year; October: Text editing and proofing process Design concepts; November: Course listings from WPM (call for updates comes from Admissions in early November); December: Proofing of courses; January: Final sign off from stakeholders; February: Print Delivery
Arrival Guide | November: Kick off meeting; December: Design concepts Copyediting; January: Copyediting Proofing; February: Proofing Sign off; March: Print Delivery
Postgraduate Prospectus | January: Kick off meeting / discussions re format; February: Upload to Sharepoint for updating by Schools and teams; March: Text editing and proofing process Design concepts; April: Schools update course info on WPM Proofing process; May: PDFs to contributors; June: Final sign off from stakeholders; July: Print Delivery
Good luck postcard and digital campaign | February: Brainstorm ideas, design concepts; March: Proofing Data gathering; April: Prrofing Sign off and print; May: Distribution e-versions sent
Get Ready Guide | March: Kick off meeting / discuss successes/ issues of last year; April: Text editing Design concepts; May: Text editing and proofing process; June: Proofing process; July: Print Delivery
Welcome Operational planning and meetings | September: Final meetings Welcome; March: First meeting; April: Ongoing meetings Review of yast year's events and feedback; May: Refine and plan events; June: Feed into What's on guide; July: Meet to check details; August: Meet to check details
What's On Guide | April: Kick off meeting / discuss successes/ issues of last year; May: Text editing and proofing process Design concepts; June: Proofing process; July: Print Delivery
Confirmation & Clearing content on corporate website | April: Kick off meeting / discuss successes/ issues of last year; May: Development; June: Sign-off; July: Early clearing starts
Confirmation & Clearing staff view site development | April: Kick off meeting / discuss successes/ issues of last year; May: Development; June: Sign-off; July: Early clearing starts
Undergraduate Prospectus | Deadline for Schools and teams for course detail copy | Schools asked to update A level and IB entry requirements on WPM Design concepts | Deadline for A level and IB entry requirements | Schools asked to update additional entry requirements on WPM 1st design proofs | Early Jan deadline for additional entry requirements All WPM information updated ready for course profiles rollover Late Jan final sign off from stakeholders | Print Delivery |  | Kick off meeting / discuss successes/ issues of last year | Upload to Sharepoint for updating by Schools and teams | Updating by Schools and teams | Updating by Schools and teams | Updating by Schools and teams
International Undergraduate Prospectus | Deadline for Schools and teams for course detail copy | Schools asked to update A level and IB entry requirements on WPM Design concepts | Deadline for A level and IB entry requirements | Schools asked to update additional entry requirements on WPM 1st design proofs | Early Jan deadline for additional entry requirements All WPM information updated ready for course profiles rollover Late Jan final sign off from stakeholders | Print Delivery |  | Kick off meeting / discuss successes/ issues of last year | Upload to Sharepoint for updating by Schools and teams | Updating by Schools and teams | Updating by Schools and teams | Updating by Schools and teams
Decliner survey | April: UG survey starts (fortnightly); May: PG survey starts (fortnightly); June: Both sent fortnightly; July: Both sent fortnightly; August: UG stops early August PG stops late August
My Manchester publication | September: Proofing Sign off; October: Print, delivery; May: Kick off meeting / discuss successes/ issues of last year; June: Contributors to edit, source profiles and photography; July: Text editing and proofing process Design concepts; August: PDFs to contributors 2nd proofs out Sign off from contributors & stakeholders
Offer letter leaflet | September: Proofing Sign off; October: Print, delivery; June: Kick off meeting / discuss successes/ issues of last year; July: Text editing and proofing process Design concepts; August: Design and proofing
Ask me for staff comms plan | September: Implementation; June: Kick off meeting / discuss successes/ issues of last year; July: Consultation Web development; August: Implementation
Luggage tags | July: Review last year, consider redesign; August: Sign off and print
My Manchester news e-newsletter | Issue 11 (moves over to current student format) Review | Review | Issue 1 | Issue 2 | Issue 3 | Issue 4 | Issue 5 | Issue 6 | Issue 7 | Issue 8 | Issue 9 | Issue 10
RAID bullein | Ongoing (fortnightly) | Ongoing (fortnightly) | Ongoing (fortnightly) | Ongoing (fortnightly) | Ongoing (fortnightly) | Ongoing (fortnightly) | Ongoing (fortnightly) | Ongoing (fortnightly) | Ongoing (fortnightly) | Ongoing (fortnightly) | Ongoing (fortnightly) | Ongoing (fortnightly)
Key
SC&M projects (some input required by other teams)
Projects with input required from Schools