## Slide 1: Creating a Communications Plan
http://www.staffnet.manchester.ac.uk/services/change-management-process-improvement/
July 2016

## Slide 2: Why create a communications plan?
A communication plan is required for the change team to agree how the change will be communicated to the key stakeholders identified in the stakeholder matrix.

## Slide 3: What you need before you start
A stakeholder matrix

## Slide 4: How to create a Communications Plan #1
Review where stakeholders are placed on the matrix of ‘Support for change’ x ‘Influence over others in this change’ and what type of communication would be suitable e.g. Involve, Partner, Inform, Consult
Review the ‘Types of Communication’ on slide 4, add your own suggestions

## Slide 5: Types of Communication
INVOLVE Open conversations Invitations to attend steering committee meetings | PARTNER Include in Steering Committee membership Assign Champion role for specialist advisors
INFORM Website links Provide web dates Newsletters | CONSULT Focus groups Workshops Questionnaires/ Surveys Question and Answer sessions

## Slide 6: How to create a Communications Plan #2
Use a large whiteboard or paper roll to create an outline of a Communications Plan (slide 7)
Create a post-it for each Stakeholder and place the first one in the column ‘Who’
For the first Stakeholder identify ‘Why’ you need to communicate to them, identify ‘What’ you need to communicate, and then ‘How’ and ‘When’. Use post-its so you can move content around
Continue until the communication needs of all Stakeholders have been clarified

## Slide 7: Communications Plan
Who? | Why? | What? | How? | When?

## Slide 8: Communications Plan
A communication plan doesn’t have to be complicated, above is an example of a simple communications plan