FBMH Social Responsibility Public Engagement Forum

Action Plan: 2017- 2018

- Background

The University of Manchester is unique in having social responsibility (SR) as one of its three core goals; no other UK University affords it this level of strategic priority. The Faculty’s vision for social responsibility is that we will empower people to transform their ideas in biology, medicine and health for the benefit of society in Manchester, the UK and across the globe. The Faculty’s SR strategy consists of seven key areas: communications, engaging our communities (public engagement), research with impact, socially responsible graduates, equality, diversity and inclusion, environmental sustainability and succession planning. Excellent public engagement (including patient and public involvement: PPI) is critical to achieving our goal to embed social responsibility in our research and teaching, providing multiple gains for all. This document sets out the action plan for the Social Responsibility Public Engagement forum for 2017/18 to support the Faculty SR strategy2, the University Public Engagement plan and the Inspiring our Communities strategy. Progress will be reviewed and reported through the forum and additions/amendments made as required.

Action Plan: 2017- 2018

|  | Objective | Action | Who | When | Status (Red, Amber or Green) |
| --- | --- | --- | --- | --- | --- |
|  | Communications |  |  |  |  |
| 1 | Establish a high public engagement profile for research and learning | - Publish 5 high impact articles (both peer reviewed academic journals and/or popular science/general media) |  | - By 2022, with 2 in 2017/2018 | - Green: ‘Science Communication in the field of fundamental biomedical research’ |
| 2 | Showcase public engagement achievements internally/externally | - Hold Public Contributor Celebratory event - Faculty awards for outstanding contribution - Making a Difference Awards nominations - Achieve >1 shortlisted entry for external award (e.g. NCCPE) |  | - July 2018 - July 2018 - Jan 2018 - 2018 | - Amber: Planned - Amber: Planned for 2018 - Amber: Deadline Jan 22nd 2018 - Amber: Planned for 2018 |
| 3 | Communicate the positive impact of our public engagement activities | - Magazine - Webpage - Engagement@manchester network - Journal articles/conferences (e.g. INVOLVE and NCCPE) |  | - Jan 2018 - 2018 - Jan 2018 - Ongoing | - Green: Special issue Jan 2018 - Amber: Revision planned 2018 - Planned (SR in curriculum) - TBC |
| 4 | Establish and embed effective communication channels | - Establish Public Contributor communications network with 150 members by 2018 - 10% of staff registered to receive key social responsibility communications by 2018 |  | - Ongoing - Ongoing | - Amber - Green |
|  | Engaging our Communities |  |  |  |  |
| 5 | Lead the Faculty’s activities in relation to Institutional ‘Inspiring Communities’ social engagement and Public Engagement Plans | - Contribute to the Community Festival - Pump-prime projects through ‘Engaging our Communities funding’ - Submit PE bid to Wellcome Trust - Support our history and heritage, through Museum Medicine and Health: NHS’ first 70 years and UoM exhibition - Lead on International Women’s Day event - Develop PE standards |  | - Expressions Interest Jan ‘18 - Dec 2017 - Ongoing - Ongoing - 5th March 2018 - Feb 2018 | - Amber - Green: 7 awarded - Amber - Amber - Amber - Amber |
| 6 | Partnership working | - Evolve a common PPIE strategy across the entire Health Innovation Manchester footprint |  | - Ongoing | - Amber |
| 7 | Embed PPIE within core teaching and learning | - SR in the curriculum work programme, enabling 250 students annually |  | - Dec 2017 | - Green: 6 awarded |
| 8 | 100% of eligible grant applications to include PPI as integral component to the proposed project by 2021 | - Establish grant support network? |  | - TBC | - TBC |
| 9 | Lead at least one policy@manchester event annually, focusing on major health challenges, increasing to three by 2022 | - Identify themes and contributors (e.g. NHS reform, devoHealth, SR in curriculum and changing landscape Higher Education etc.) |  | - Ongoing | - Amber |
|  | Training and Support |  |  |  |  |
| 10 | Ensure Public Contributors are welcomed and introduced to the Faculty | - Develop Public Contributor Induction Pack |  | - Feb 2018 | - Green |
| 11 | All PE staff/public contributors are supported and trained/mentored | - Public Engagement governance - PPI workshop - PPI training: intro, comms skills, setting up PPI group - Train 30 staff/students/public contributors - Establish PE practitioner scheme - Evaluate training |  | - Feb 2018 - Feb 2018 - Ongoing - Ongoing - Ongoing - Ongoing | - Green - Green - Green - Amber - Amber - Amber |
|  | Measuring the Impact: Evaluation |  |  |  |  |
| 12 | All public engagement is adequately evaluated | - Develop Faculty evaluation framework |  | - April 2018 | Amber |

Formerly the Centre for Engagement and Involvement (CEI) Forum

Available at: http://documents.manchester.ac.uk/display.aspx?DocID=35221

Share, Inspire, Involve: Public Engagement strategy 2017-2020 http://www.engagement.manchester.ac.uk/about/Public%20Engagement%20Strategy%20FINAL.pdf

Inspiring Communities: Local community social engagement plan 2016-2019 (http://documents.manchester.ac.uk/display.aspx?DocID=30998)

http://www.sciencedirect.com/science/journal/10849521/70/supp/C?sdc=1

NCCPE: National Co-ordinating Centre for Public Engagement https://www.publicengagement.ac.uk/work-with-us/engage-competition-2016

Inspiring Communities: Local community social engagement plan 2016-2019 (http://documents.manchester.ac.uk/display.aspx?DocID=30998)

Share, Inspire, Involve: Public Engagement strategy 2017-2020 http://www.engagement.manchester.ac.uk/about/Public%20Engagement%20Strategy%20FINAL.pdf