## Approach
Benefits Realisation Approach
1. What are benefits and why do we measure them
Business change is typically proposed to achieve a more desired outcome. Benefits are the specific and measurable expression of these outcomes. For example, if an organisation wants to be financially sustainable to enable research, we may need to reduce our spending in specific areas.
Benefits are defined as positive improvements from a baseline current status to an anticipated or optimum target in a specified timescale.
Financial benefits are those benefits which are related to financial outcomes including savings, income and contribution. For example, a savings benefit may take the current spend on external consultancy of £15m and anticipate a spend decrease to £5m over a 3 year period.
Non-financial benefits are those benefits which are related to non-financial outcomes and cover a very wide range of performance indicators, including process efficiency, increase in research citiations, student satisfaction with their courses, number of students applying for a course, and so on.
Dis-benefits are defined as acknowledged negative impacts expected to the baseline current status which may be anticipated with a change; these may be time-constrained or accepted as long term.
Investment and contingency budgets are the most typical type of financial dis-benefit. For example, a short term contingency spend on additional resourcing to deliver a project and mitigate risk of slippage would be deemed a dis-benefit. As many people find it confusing to consider investment as a dis-benefit, it is usually expressed as a benefit.
Non-financial dis-benefits can also happen such as a short term impact to employee satisfaction during a major period of change or a short term inefficiency when a new system is introduced before the team adjusts.
Tangible benefits are those which can be tracked directly; intangible benefits are those where the change may only contribute indirectly or as part of a broader set of actions.
Benefits determine whya change project is approved and continued. Benefits realisation covers the identification and managing of benefits across a project. Both benefits and dis-benefits should be considered when assessing the realisation of benefits.
Formal management of benefits realisation is stated project management best practice in all commonly known methodologies (PRINCE2, PM Book of Knowledge, and APM). The project proposes to follow best practice and tailor as required to fit the University of Manchester’s current technical, business process and management information capability. It will also comply with any portfolio or programme requirements associated with the management of benefits.
2. The key role of benefits within the project
It is proposed that benefits are used within the project to:
1. Ensure the change will contribute to strategic vision and goals through clear identification of benefits within a business case
All change activity should be considered and challenged on whether it is contributing to the strategic vision of the University.
The benefits approved by the Project Board are detailed in this document along with how each will be measured and tracked.
2. Determine whether the project should be continued during regular project checkpoints to assess if the proposed benefits are still relevant
All change activity should be subject to challenge on whether it is worth beginning or continuing through an assessment of the benefits at key points. For example, a change of scope may reduce the benefit savings or expected process efficiency. According to the programme methodology, if it is clear that the change will not provide the expected benefits at any stage, it must be replanned or stopped.
The project is committed to reviewing benefits at the following checkpoints:
· At Design & Plan completion: DD/MM/YYYY
· During Implementation prior to launch: DD/MM/YYYY
3. Assess the overall success of the proposed change through continued benefits realisation beyond the duration of the project through continued monitoring of identified measures through the PMO’s quarterly reporting to the Programme Management Board or other operating reporting mechanism
Beyond the project, the change benefits will continue to be tracked. This will enable the overall success of the project and the change to be assessed.
The Change Sponsor e.g. Director of IT will be accountable for tracking the expected benefits of the change until the benefit is realised or can no longer be tracked effectively due to future change activity. They may delegate the responsibility to the role which will track benefits.
Financial and non-financial benefits associated with M2020 targets will be reported through the Programme Pack created by the PMO for review by the Programme Management Board which reports to the Finance Sub-Committee (FSC). Full reports will be provided on a quarterly basis in line with financial forecasting with any major known variance reported monthly.
3. Tracking Benefits
All benefits will be tracked through a Benefits Realisation Log. This is a spreadsheet which will document:
· Each benefit or dis-benefit
· The method of measurement and assessment
· The baseline pre-change
· The target post-change
· The timescales within which the benefit should be realised
· The next review date
· Status at the last review date
The log will be a deliverable of the project and handed over to the change sponsor at the close of the project.

## Benefit Realisation Log
Benefits Realisation Log |  |  |  |  | Confidential & Commercially Sensitive - Password protect if necessary
This worksheet tracks all benefits and dis-benefits associated with the change from identification through to realisation
Dis-benefits will be referred to as benefits but they will have a target lower than baseline
Project Name |  | Name of the project
Change Sponsor |  | Name and role of the sponsor
Business Change Manager |  | Name of the person responsible for delivering the change
Benefit or Dis-benefit | Description | Tangible/ Intangible | Financial/Non-Financial | Method of measurement or assessment | Baseline (before change) | Target (ideal post change) | Timescale for benefit to be realised or known due date | Benefit Realisation Owner | Next Review Date | Status at last Review | Link to supporting documentation | Comments
Benefit | e.g. Increased time with budget holders | Tangible | Financial | Time with budget holders | 1 hour | 2 hours | Within 1 month | Deputy Director of Finance | 2018-08-20 | On track | Business case
Dis-benefit | e.g. Initial decrease in staff satisfaction following change | Intangible | Non-financial | Staff survey Q27 | 73% | 60% | Within 1 month | Director of HR | 2018-08-20 | On track | Closure report

## Document Information
Benefits Realisation Log
This document is a working document to track the benefits associated with the change
Benefits are identified at the beginning of the change. During a project they should be assessed at each stage to ensure they are still relevant.
The log should be reviewed by the Change/Project Sponsor, the Business Change Manager, and the Project Manager during the life of delivery project;
by the Sponsor and Business Change Manager before and post the delivery project
It will be maintained by either the BCM on behalf of the sponsor
Document Information
Document Owner
Name of the sponsor and role, e.g. Russell Ashworth, Programme Director
Author | Role | Version | Date

## How to use this template
How to use this template
Benefits Realisation Log
Benefit & Disbenefit | Whether it is a benefit or disbenefit
Description | The specific benefit
Tangible/Intangible | The ability to track the benefit directly
Financial/Non-Financial | The type of benefit
Method of measurement or assessment | The way the benefit will be measured or assessed
Baseline (before change) | The baseline measurement or assessment prior to the change
Target (ideal post change) | The target achievement
Timescale for benefit to be realised or known due date | Choose from the drop-down list - see reference tab
Benefit Realisation Owner | The owner accountable for realising the benefit
Next Review Date | Date of the next review
Status at last Review | Choose from the drop-down list - see reference tab
Link to supporting documentation | Link to business case, project closure report, benefits report
Comments | Any comments about the benefit
Document Information
Document Owner | Name and role of the sponsor
Author | The person updating the log
Role | The role of the person updating
Version | Version number
Date | Date updated
You can delete this tab once you have finished completing the first version

## Reference
Status | Tangible | Change can be directly associated as a causal reason for improvement | Timescales
Not due | Intangible | Change cannot be directly associated as a causal reason for improvement but may contribute | Within 1 month
Off track |  |  | Within 3 months
At risk | Financial | Change is associated with budget | Within 6 months
On track | Non-financial | Change is not associated with budget but another key performance indicator | Within 1 year
Complete |  |  | Within 18 months
| Benefit | The outcome wanted | Within 2 years
| Dis-benefit | A known disadvantage provoked by the change