## Template Guidance

| ### Go to Green Plan | Individual plans detailing how any remaining issue will be tackled to ensure the change is realised beyond the project |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Use in… | Leading change |  | Engaging people in change |  |  | Making change happen |  |
| Why would I create this? | It is not always possible for every issue in a change implementation to be completed before the end of the project. While critical issues should definitely be addressed, non-critical issues may still be in evidence and handled through temporary workarounds. A Go to Green plan provides a handover document from the project into business-as-usual to enable them to complete resolution post the project. |  |  |  |  |  |  |
| What is the content? | The document details the issue(s) outstanding, the current workaround, the required actions to address, who owns these actions, an estimated timeframe for completion. The Go to Green plan should be agreed with the Change Sponsor as part of the project closure. |  |  |  |  |  |  |
| Who owns this? | Change Sponsor |  |  |  |  |  |  |
| Who typically will be responsible? | Business Lead or Business Change Manager or Project Manager (acting as BCM) |  |  |  |  |  |  |
| Phase of change | Embed |  |  | Project Stage |  |  | Close |
| Tips on tailoring |  |  |  |  |  |  |  |
| Small Create a Go to Green plan or ensure the actions are incorporated into business as usual action logs or operational reporting |  | Medium Create Go to Green plan |  |  | Large Create Go to Green plan |  |  |

For the rest of the document, text in italics should be replaced with the required content. Please note the examples are illustrative and have fictional data. Complete as much information as possible.

# Go to Green Plan

| Faculty, School, Division, Directorate Name | The organisation sponsoring the change |
| --- | --- |
| Change Sponsor | Name of the individual who will lead and be accountable for the change |
| Business Lead or Business Change Manager | Name of the individual who will be responsible for delivering the change |
| Author | Name of the individual writing the document |
| Date and Version | DD/MM/YY – DRAFT v0.1 (final should be reflected as FINAL v1.0) |

## Introduction

The purpose of this document is to provide a plan for any non-critical issue remaining at the close of a project.

The project manager ensures these are documented and handed over to the Business Change Manager or the Business Lead, and Change Sponsor.

The Go to Green Issue section should be repeated as many times as necessary – or if only 1 issue remains, delete the second section.

## Go to Green: Issue

| Issue Title | For example: Head of School has not been recruited |  |  |
| --- | --- | --- | --- |
| Issue Description | For example: The Head of School role has not been filled during the project recruitment round |  |  |
| Issue Owner | For example: Faculty Dean |  |  |
| Actions to date | For example: Interim Head of School appointed. Agency has been engaged to find suitable candidates. |  |  |
| Actions required to resolve | Action | Owner | Date to be complete |
|  | For example: Complete recruitment by December 2018 |  |  |
| Any further comments |  |  |  |
| Links to information |  |  |  |

## Go to Green: Issue Title 2

| Issue Title |  |  |  |
| --- | --- | --- | --- |
| Issue Description |  |  |  |
| Issue Owner |  |  |  |
| Actions to date |  |  |  |
| Actions required to resolve | Action | Owner | Date to be complete |
| Any further comments |  |  |  |
| Links to information |  |  |  |