## Transition Plan
Transition Plan |  |  |  | Confidential - Password protect if necessary
This worksheet tracks all transition actions required for a smooth handover from the project into business-as-usual. Alternatively, include in the master project plan
Actions in italics are to help prompt thinking only; delate any not appropriate and add any which are not included but required
Project Name | Name of the project
Change Sponsor | Name and role of the sponsor
Business Change Manager | Name of the person responsible for delivering the change
Project Manager | Name of the project manager
Action Required | Action Owner | When | Planned Completion Date | Comments, Issues, Queries | Status | Completion Date
Strategy
New strategic vision to be created |  | Implementation
New strategic plan to be created |  | Implementation
New strategic owner to be identified |  | Pre-Implementation
Revision to operational priorities |  | Implementation
Revision to budget (annual) |  | Pre-Implementation
Revision to budget (5 year) |  | Pre-Implementation
Shared Values
New shared values to be created |  | Implementation
Shared values to be revised |  | Implementation
Style
New leadership behaviours to be created |  | Implementation
Leadership programme to be created/revised |  | Implementation
Structure
Create/updated organisational hierarchy document |  | Pre-Implementation
Create any mandatory legal notices |  | Pre-Implementation
Discuss with Trade Unions, other key stakeholders |  | Pre-Implementation
Obtain governance approvals |  | Pre-Implementation
Announce formal consultation |  | Pre-Implementation
Finalise job descriptions |  | Pre-Implementation
Obtain HERA profiles |  | Pre-Implementation
Create and approve PCMs |  | Pre-Implementation
Staff
Prepare for recruitment |  | Pre-Implementation
Recruitment - interviews held |  | Implementation
Recruitment - roles appointed |  | Implementation
Recruitment - new starters induction |  | Business Cutover
Recruitment - new starters onboarding |  | Business Cutover
Implement line management changes |  | Business Cutover
Implement staff communications plan |  | Pre-Implementation
Skills
Confirm training needs analysis is complete |  | Pre-Implementation
Plan training |  | Pre-Implementation
Create training material |  | Implementation
Update existing training material |  | Implementation
Run pilot training |  | Implementation
Deliver training |  | Business Cutover
Review training feedback |  | Business Cutover
Run mop-up training for non-attendees/new starters |  | Post launch
Assess whether additional training is required |  | Post launch
Systems - Business processes
Create/revise business processes |  | Implementation
Create/revise local policies |  | Implementation
Create/revise local procedures |  | Implementation
Identify critical processes for monitoring |  | Implementation
Monitor critical business processes |  | Post launch
Systems - Management Information
Document business reporting requirements |  | Pre-Implementation
Create/revise business operational reporting |  | Implementation
Create/revise reporting tools |  | Implementation
Create/revise reporting dashboard(s) |  | Implementation
Migrate reports |  | Business Cutover
Systems - IT
Document business requirements/user stories |  | Pre-Implementation
Agree solution designs |  | Implementation
Obtain licences |  | Implementation
Agree security matrix |  | Implementation
Agree SLAs/supplier contracts |  | Implementation
Create User Acceptance Test Approach & Plan |  | Implementation
Create User Acceptance Scenarios |  | Implementation
Create User Acceptance Test Schedule |  | Implementation
Agree data map & dictionary |  | Implementation
Cleanse data ready for migration |  | Implementation
Rehearse data migration |  | Implementation
Systems - Information Governance
Create/revise document management system |  | Pre-Implementation
Create new shared folders / Sharepoint site |  | Implementation
Delete/archive old shared folders |  | Implementation
Migrate documents from current to future shared folders/Sharepoint |  | Business Cutover
Agree security matrix |  | Implementation
Request new mailbox and access |  | Implementation
Clear down/archive old mailboxes |  | Implementation
Request new telephone hunt group and access |  | Implementation
Request old telephone hunt groups be discontinued |  | Implementation
Clear out paper documentation |  | Post launch
Archive required retained documentation |  | Post launch
Create/revise local data management system |  | Pre-Implementation
Delete/archive old data |  | Implementation
Cleanse data |  | Implementation
Migrate data |  | Business Cutover
Stakeholders
Stakeholders analysed |  | Pre-Implementation
Gap analysis performed for stakeholders |  | Pre-Implementation
Stakeholder communication |  | Pre-Implementation
Agree plan for revision of documents with stakeholder A |  | Implementation
End of plan

## Document Information
Transition Plan
This document is a working document to track the specific actions required to transition the organisation from current to future state
It should be reviewed on a regular basis by the Change/Project Sponsor, the Business Change Manager, the Project Manager, and Business Analyst if assigned
It will be maintained by either the BCM or PM on behalf of the sponsor
It is highly recommended that this document be password protected
Document Information
Document Owner
Name of the sponsor and role, e.g. Russell Ashworth, Programme Director
Author | Role | Version | Date

## How to use this template
How to use this template
Transition Plan
Action Required | The specific action required
Action Owner | The owner of the action
When | Choose from the drop-down list - see reference tab
Planned Completion Date | Date the action should be completed by
Comments, Issues, Queries | Any free format comments, issues or queries
Status | Choose from the drop-down list - see reference tab
Completion date | Date the action completed
Document Information
Document Owner | Name and role of the sponsor
Author | The person updating the plan
Role | The role of the person updating
Version | Version number
Date | Date updated
It is highly recommended that this document be password protected
You can delete this tab once you have finished completing the first version

## Reference
When | Status
Pre-Implementation | Not due
Implementation | Off track
Business Cutover | At risk
Day of launch | On track
Post launch | Complete