FBMH Social Responsibility Public Engagement Forum

Action Plan: 2018-2019

- Background

The University of Manchester is unique in having social responsibility (SR) as one of its three core goals; no other UK University affords it this level of strategic priority. The Faculty’s vision for social responsibility is that we will empower people to transform their ideas in biology, medicine and health for the benefit of society in Manchester, the UK and across the globe. The Faculty’s SR strategy consists of seven key areas: communications, engaging our communities (public engagement), research with impact, socially responsible graduates, equality, diversity and inclusion, environmental sustainability and succession planning. Excellent public engagement (including patient and public involvement: PPI) is critical to achieving our goal to embed social responsibility in our research and teaching, providing multiple gains for all. This document sets out the action plan for the Social Responsibility Public Engagement forum for 2018/19 to support the Faculty SR strategy2, the University Public Engagement plan and the Inspiring our Communities strategy. Progress will be reviewed and reported through the forum and additions/amendments made as required.

Action Plan: 2018-2019

|  | Objective | Action | Who | When | Status (Red, Amber or Green) |
| --- | --- | --- | --- | --- | --- |
|  | Communications |  |  |  |  |
| 1 | Develop a Social Responsibility Communications plan | - Review current FBMH Social Responsibility communications and develop a draft communications plan to present at the January forum | NL | - March 2019 |  |
| 2 | Establish a high public engagement profile for research and learning | - Publish 8 high impact articles (both peer reviewed academic journals and/or popular science/general media) | All | - By 2022, with 4 in 2018/2019 |  |
| 3 | Showcase public engagement achievements internally/externally | - Hold annual Public Contributor Celebratory event - Host Faculty awards for outstanding contribution to PPIE - Making a Difference Awards nominations - Achieve >1 shortlisted entry for external award (e.g. NCCPE) - Showcase projects funded by the ‘Engaging our Communities’ fund - Coverage of public engagement-related stories picked up by regional, national and international media | SF SF SRPE SRPE SF SF | - July 2019 - July 2019 - Jan 2019 - Dec 2019 - Dec 2018 - Dec 2019 | - Green – Gold NCCPE Engage watermark Nov 2018 |
| 4 | Communicate the positive impact of our public engagement activities | - Magazine – distribute new editions of the Social Responsibility magazine (2/3 editions a year) - Webpage – promote revised webpages through PPIE channels and continue to add resources and promote content to researchers and public contributors - Engagement@manchester network - Journal articles/conferences (e.g. INVOLVE and NCCPE) | NL NL SF | - Sept 2018 and 2019 - Sept 2018-Feb 2019 - Dec 2019 - Dec 2019 | - Green - Amber – ongoing |
| 5 | Establish and embed effective communication channels for public engagement successes | - Revise public engagement communications network and establish 200 members by end of 2018 and 250 by July 2019 (target 450 by 2022) - 15% of staff registered to receive key social responsibility communications increasing to 25% by 2022 (3200 staff = 480) • Ensure active promotion and signposting of support and resources within the Faculty and University | SF SF & NL SF | - Dec 2018 July 2019 - July 2019 - Dec 2019 | - Green |
|  | Engaging our Communities |  |  |  |  |
| 6 | Lead the Faculty’s activities in relation to Institutional ‘Inspiring Communities’ social engagement and Public Engagement Plans | - Contribute to the Community Festival with all schools and Divisions represented - Pump-prime projects through ‘Engaging our Communities funding’ - Submit PE bid to Wellcome Trust - Support our history and heritage, through Museum Medicine and Health, holding >5 engagements events and embedding the ‘Instruments of change’ exhibition in our research and teaching - tours and open days - Lead on Faculty International Men’s day and International Women’s Day events | NL SRPE Team BR NL | - June 2019 - Dec 2018 - 2018 - Launch event held in 2018 2 events 2019 - Nov 2018 and March 2019 | - Green - Green (launch event) - Green – digital campaign |
| 7 | Partnership working with patients and the public and HInM | - Evolve a common PPIE strategy across the entire Health Innovation Manchester footprint | HW | - Initial discussions to be held 2019 |  |
| 8 | Embed PPIE within core teaching and learning (SR in the curriculum funding) | - SR in the curriculum work programme, enabling 250 students annually, with key focus on Widening Participation8 (WP) activity |  | - Dec 2018 |  |
| 9 | 100% of eligible grant applications related to Social Responsibility to include PPI as integral component to the proposed project by 2021 | - Establish PPIE grant support network - Create criteria for an eligible grant application in relation to PPIE |  | - 2019/20 - 2019/20 |  |
| 10 | Lead on at least one policy@manchester event annually, focusing on major health challenges, increasing to three by 2022 | - Identify themes and contributors for events (e.g. NHS reform, devoHealth, SR in curriculum and changing landscape Higher Education etc.) Impact on more than 2000 members of our local community by 2022. | SRPE | - 2019 |  |
| 11 | Establish Faculty PPIE group as a resource for Faculty researchers and teachers | - Call-out for public contributors who are interested in becoming a member of the PPIE group - Establish terms of reference and chair for group - Promote PPIE group to researchers and teachers within the Faculty. | SF SF SF | - Oct-Dec 2018 - Jan 2019 - Jan-March 2019 | - Green - Green |
|  | Training, Support and Resources |  |  |  |  |
| 13 | Ensure Public Contributors are welcomed and introduced to the Faculty | - Host two induction sessions per year - Distribute and promote the Public Contributor Induction Packs to public contributors and researchers within the Faculty (Vice-Dean message, website, announcements etc) and external stakeholders (e.g. NHS Trusts, charities) to enable diversification and increase in Public Contribution |  | - Sept 2018 & February 2019 - Sept 2018-Jan 2019 | - Green - Green - Green - ongoing |
| 14 | All PE staff/public contributors are supported and trained/mentored | - Develop/Host a series of PPIE training for public contributors: Induction Session, social media, equality and diversity, IT skills - Develop/Host a series of training for staff: setting up PPI group, comms skills, evaluating public engagement, introduction to PPIE - Train 30 staff /students/public contributors - >10 Faculty staff/students to join the University Public Engagement Champion network - Evaluate training - Create researcher checklist (what to include when conducting PPIE, what is the best PPIE to use) | SF HW & SF HW & SF SF SF & SJ | - Feb 2019 - July 2019 - July 2019 - July 2019 - July 2019 - July 2019 |  |
| 15 | Streamline Faculty systems and processes for public contributors (Volunteer lifecycle) | - Liaise with Faculty HR partner regarding systems and processes for public contributors - Establish a University status for public contributors and associated processes with a nominated contact/facilitator - Establish public contributor database with HR - Develop Joint PPIE initiatives with other Faculties | SF & HW | - Sept-July 2019 - July 2019 - Ongoing - July 2019 |  |
|  | Measuring the Impact: Evaluation |  |  |  |  |
| 16 | All public engagement is adequately evaluated | - Develop a Faculty evaluation framework | SF | - 2019 |  |

Glossary

Environmental sustainability describes the way we use our knowledge and influence to ensure that our research, staff and graduates lead the way to a sustainable world.

Equality, diversity and inclusion, describes the way the University is committed to providing an environment free from discrimination, bullying, harassment or victimisation, where all members of its community are treated with respect and dignity. It aims to create a culture of diversity within its community, providing a dynamic working and learning environment, where all members are valued for their contribution and individuality.

Public engagement describes the ways in which higher education and research can be shared with the public,

Public Involvement is an active partnership between research or teaching staff and patients or members of the public.

Public Contributor commonly describes members of the public involved and engaged in our teaching and research.

Research with impact describes the way our research has the potential to have a positive difference to society by addressing the major challenges we face in the 21st Century.

Socially responsible graduates describes the way our graduates learn to exercise ethical, social and environmental responsibility.  Our students are supported by the Faculty by encouraging them to get involved and start their own projects.

Social Responsibility describes the way we are making a difference to the social and economic well-being of our communities through our teaching, research, and public events and activities.

Widening participation enables fairer access to a Manchester education for talented students regardless of their background. The University is proud to lead the Russell Group in having the highest number of students form areas of low participation in higher education and from lower socio-economic backgrounds combined.

Formerly the Centre for Engagement and Involvement (CEI) Forum

Available at: http://documents.manchester.ac.uk/display.aspx?DocID=35221

Share, Inspire, Involve: Public Engagement strategy 2017-2020 http://www.engagement.manchester.ac.uk/about/Public%20Engagement%20Strategy%20FINAL.pdf

Inspiring Communities: Local community social engagement plan 2016-2019 (http://documents.manchester.ac.uk/display.aspx?DocID=30998)

NCCPE: National Co-ordinating Centre for Public Engagement https://www.publicengagement.ac.uk/work-with-us/engage-competition-2016

Inspiring Communities: Local community social engagement plan 2016-2019 (http://documents.manchester.ac.uk/display.aspx?DocID=30998)

Share, Inspire, Involve: Public Engagement strategy 2017-2020 http://www.engagement.manchester.ac.uk/about/Public%20Engagement%20Strategy%20FINAL.pdf

8 Widening Participation annual report 2017 http://documents.manchester.ac.uk/display.aspx?DocID=4294