# Manchester Online – timeline

Accessible plain-text version of the visual timeline.

# Timeline overview

2026: Phase: Implement and prepare. Milestone: Project mobilisation.

April 2027: Year one: Launch, stabilise and prove. Milestone: First intake launch.

2028: Year two: Scale and optimise. Milestone: Expand portfolio.

# 2026: Phase: Implement and prepare

## Key activities

Mobilise with Flex Partner

Complete systems integration

Finalise academic model

Deliver recruitment readiness

Prepare admissions and support services

# April 2027: Year one: Launch, stabilise and prove

## Key activities

Deliver initial portfolio and onboard first cohorts

Stabilise operations across University and Partner

Embed academic delivery model and tutor framework

Establish performance, data and reporting foundations

# 2028: Year two: Scale and optimise

## Key activities

Grow enrolments across intake cycles, with six intakes per year, and across programmes

Transition to a fully configured, scalable operating model

Improve efficiency and student outcomes

Increase University control of key capabilities